Post Award Conference Meeting Agenda ESPC Process Doc. P4-02

Rev. 08-27-18

Responsibility: PF

# Post-Award Conference Meeting Agenda

# (minimum topics required to be covered are listed)

## Introductions/Roles

- Welcome by agency contracting officer (or designated chairperson)

- Introductions

- Objectives of the meeting

  - Achieve a clear and mutual understanding of all contract requirements

  - Continuity and transitions from pre-award to post-award to be included in each discussion below.  People, responsibilities, work, etc.

  - Identify and resolve potential problems

  - Not intended to change the contract, but should identify and clarify ambiguities

  - Provide written documentation on areas requiring resolution, controversial matters, participants assigned responsibilities for further actions, and due dates (who, what, where, when, and why within contractual schedule).

## Roles, Responsibilities, Authority of each person

- Procurement Contracting Officer/Administrative Contracting Officer

- Agency Contracting Officers Representative (delegation of authority)

- Other agency key personnel (including M&V witnessing)

- ESCO primary point of contact

- Other ESCO Key personnel

- ESCO’s key subcontractor personnel (as applicable) – (the ESCO is responsible for subcontractors and the government has no privity)

- As applicable, review Tri-Party Agreement or M&O type agreements

## Communication Protocols

- Communication roles and responsibilities

  - ESCO to feds and feds to ESCO

  - Gatekeepers agency CO/COR are primary POCs

  - Gatekeepers identify the ESCO primary POC

- 2 week/30/60/90 day look ahead discussion

- Process, emails, approvals, etc.

- Emergency notification process

- Site access requirements and security (including cyber when applicable)

## Task Order Contract Terms and Conditions

- Ensure mutual understanding off all task order contract terms and conditions

  - Project scope (include coordination with needed agency POCs, e.g., facilities, utilities, operations, security/cyber-security, data center, resilience, etc.)

  - Performance of Energy Conservation Measures/Work Breakdown Structure

  - DOE IDIQ flow down contract clauses

  - Task order specific clauses

  - Savings guarantees

## Contract Deliverables – Post-Award (refer to IDIQ Attachment J-4)

Review status of IDIQ Attachment J-4 post-award deliverables (applicable sections in IDIQ referenced).

| - Certificate of Insurance (Sec. H.9) | - Performance Bond (Sec. H.7) | - Payment Bond (Sec. H.7) |
| --- | --- | --- |
| - Safety & Health Plan (Sec. H.10.D) | - ECM Quality Control Inspection Plan (Sec. C.5.3) | - Work Schedule (Sec. C.14) |
| - Work Outside Normal Hours (Sec. C.14) | - Design & Construction Package (Sec. C.5.1) | - Commissioning Plan (Sec. C.5.4.B) |
| - Operation Work Procedure and Checklist (Sec. C.6.B/C) | - Maintenance Work Procedure and Checklist (for each ECM; Sec. C.7.B/C) | - Notification of Utility Interruption (Sec. C.5.6) |
| - O&M Manuals and Spare Parts Lists (Sec. C.10.1) | - As-built Drawings (Sec. C.5.7) | - Commissioning Report (Sec. C.5.4.C) |
| - Post-Installation Report (Sec. C.4.2.C) | - Annual M&V Report on ECM Performance (Sec. C.4.2.D) |  |

## Project Schedule and Milestones

- Review project schedule included in ESCOs proposal

- Discuss design and design review schedule

- Discuss any known potential barriers and obstacles

- Discuss how changes to the project schedule (within scope) will be coordinated

- Plan for agency ESPC Project Manager and the Construction Manager to review the TO RFP per Sec. 11 of FEMP Best Practices guidance

## Project Design

- Review of design in awarded task order

  - Discuss what percentage of design was completed at task order award and what remains post award

- Design changes process

- ESCO design, drawings, installation plans, health and safety plan, quality control inspection plan, etc. submittal process

- Government review and approval process (including specification reviews and approvals)

  - Who performs reviews

  - Timeframes for approval

  - Discuss any known potential barriers and obstacles

## Requirements for Proceeding to Construction

- Not authorized until design have been approved by the government

- Agency to issue Notice to Proceed with Construction

## Government Acceptance

- Overall Process

- Authorities and timeframes

- Equipment title transfer and documentation

- Discuss any known potential barriers and obstacles

## Contractor Payments

- Fixed price contract

- Contract terms and conditions including task order schedules

## Reporting Requirements after Project Acceptance

- Annual post award M&V reporting

- Subcontractor reporting, other reporting

## Scope Changes, Contract Modifications, and Subsequent Phases

- Discuss process

  - Administrative

  - Within scope

  - Outside scope

  - Timing/schedule related to modifications/phases