Construction Kickoff Meeting Agenda

ESPC Process Doc. P4-01

Rev. 11-14-18

Responsibility: PF

# Construction Kickoff Meeting Agenda

# (minimum topics required to be covered are listed)

# Introductions/Roles

- Welcome by agency

- Introductions and roles of each person in the construction phase

- Objectives of the meeting

- Designate a meeting note taker

## Organization and Communications (Agency/ESCO)

- Function and authority of key agency personnel (CO, COR, other) (identify name of individuals)

- Function and authority of ESCO key personnel (identify names of individuals)

- Roles and responsibilities of agency and ESCO

  - Emergency notification process

  - Communication protocols (process, emails, approvals, etc.)

  - ESCO subcontractor oversight expectations

  - Team leads for M&V, witnessing, commissioning, and inspections (identify names)

  - Written agreement if needed (e.g., tri-party) clarifying responsibilities (personnel and costs)

## Reporting Requirements/Post Award Deliverables (Agency/ESCO)

- Ensure mutual understanding of TO requirements and deliverables

- Deliverables (refer to IDIQ contract Attachment J-4)

  - Updated organizational chart (if needed)

  - Updated implementation schedule

  - Commissioning report (should include point-to-point testing results)

  - Post-Installation M&V report

  - Davis-Bacon report (payroll statements)

  - Notification of utility interruption

  - Operation work procedure

  - Maintenance work procedure/maintenance work requirements and checklist

  - O&M manuals and spare parts lists

  - As-built drawings

  - Training

## Contract Clauses (Agency/ESCO)

- General and construction contract clauses

  - Ensure understanding of all related post award clauses associated with the construction portion of the delivery order requirements (e.g., payroll records, subcontractor requirements, Buy American Act)

  - Inspection and acceptance clauses at DOE IDIQ Section E and others added by agency (FAR 52.246-2,4,12,13,16)

- Government furnished property & contractor furnished material (applicable or not applicable)

## Site Specific, Facility Access & Security Requirements (Agency/ESCO)

- Project office/siting approval

- Contractor personnel site and/or building access requirements; non-citizen access requirements for prime and subcontractors

- Security badging process and badging/ lower-tier subcontractor list

- Escorts – process and coordination

- Restrictions/allowable equipment (e.g. cell phones, laptops and radios)

- Vehicle access approval requirements

- On and off-hour access

- Keys (If applicable)

- Vehicle licensing /registration

- Staging/lay-down yard and/or office space allocations for contractors

## Construction (ESCO)

- Construction schedule

- Schedule for construction update meetings

- Project status reports

- Plan of the Day (POD)/Plan of the Week (POW) meetings during construction (see page 3, example Agenda for POD/POW Meetings)

- Equipment data sheets

- Submittal schedule, coordination of submittal reviews, and approval process

- Preparing reviewers to ensure review readiness (ensure understanding of ESPCs)

- Project charter and/or partnering sessions (as needed)

- Weekly meetings (include subcontractors when beneficial)

- Changes and contract modifications (plan and implications)

## Safety & Environmental Planning (Agency/Site Staff)

- Site-specific safety plan, worker licensing and certifications

- Burn permit approval requirements

- Safety training

- Hazardous materials

  - Either stored or as a part of the facility, have been located and identified

  - Site specific requirements for hazardous material handling identified

  - Asbestos, MSDS, PCB’s, lead based paint, etc.

- Site injury reporting and response requirements

- Environmental permits prior to construction

- Site characterization testing, mitigation of adverse conditions, hazard monitoring (e.g., asbestos)

Quality Control and Quality Surveillance

- ESCO quality control plan (DOE IDIQ C.5.3)

  - Implementation progress

  - Testing/witnessing/other Issues

  - Changes

- Agency Surveillance

  - Verify that contract requirements are fulfilled and document performance

  - Inspections (do not relieve the contractor of responsibility)

## Permits/Outages (Agency)

- Utility service interruption permits approval

- Utility reconnect permits approval (including hot-work permits)

- Site personnel support for outages

- Service interruption scheduling

- Low voltage outage permits

- Lock-out/tag-out procedures

- Excavation/penetration permits (include indication of digging equipment) and marking boundaries

Acceptance

- Timing

- Procedures

- Roles and authority

## Example Agenda for Plan-of-Day (POD)/Plan-of-Week (POW) Meetings (ESCO)

- Objective

- Look ahead schedule (30, 60, 90 days)

- Safety

- Quality control (expectations/documentation)

- Commissioning

- Measurement and verification/witnessing (government and ESCO should understand purpose)

- As-built(s)

- Training

- Crane movements and locations reviewed for overhead hazards

- Construction start coordination requirements

- Long lead times

- Worker certifications (welding, electrical, etc.) up-to-date

- Site debris and removal

- Punch list

- Testing/inspection/acceptance (including acceptance procedures by ECM)