## Construction Scoring Matrix
Critical Decision Assessment Tool –
Traditional Construction Projects (Nuclear, Non-Nuclear), Target Scores by Project Phase
|  |  |  | Pre-Conceptual |  | Conceptual Design |  | Preliminary Design Performance Baseline |  | Final Design
|  |  |  | (CD-0) |  | (CD-1) |  | (CD-2) |  | (CD-3)
|  | Weighting Designation | Weighting Factor | Maturity Value | Target Score | Maturity Value | Target Score | Maturity Value | Target Score | Maturity Value | Target Score
A. COST
A1 | Cost Estimate | H | 7.5 | 1 | 7.5 | 2 | 15 | 5 | 37.5 | 5 | 37.5
A2 | Cost Risk/Contingency Analysis | P | 3 | 1 | 3 | 2 | 6 | 5 | 15 | 5 | 15
A3 | Funding Requirements/Profile | H | 7.5 | 1 | 7.5 | 2 | 15 | 4 | 30 | 5 | 37.5
A4 | Independent Cost/Schedule Review | P | 3 | N/A | 0 | 2 | 6 | 5 | 15 | 5 | 15
A5 | Life Cycle Cost | P | 3 | 1 | 3 | 2 | 6 | 4 | 12 | 5 | 15
A6 | Forecast Cost at Completion | P | 3 | N/A | 0 | N/A | 0 | 3 | 9 | 5 | 15
A7 | Cost Estimate for Next Phase Work Scope | P | 3 | 5 | 15 | 5 | 15 | 5 | 15 | 5 | 15
Subtotal Cost Element |  |  |  |  | 36 |  | 63 |  | 133.5 |  | 150
B. SCHEDULE
B1 | Project Schedule | H | 7.5 | 1 | 7.5 | 2 | 15 | 5 | 37.5 | 5 | 37.5
B2 | Major Milestones | P | 3 | 1 | 3 | 2 | 6 | 5 | 15 | 5 | 15
B3 | Resource Loading | P | 3 | 1 | 3 | 1 | 3 | 4 | 12 | 5 | 15
B4 | Critical Path Management | H | 7.5 | 1 | 7.5 | 1 | 7.5 | 4 | 30 | 5 | 37.5
B5 | Schedule Risk/Contingency Analysis | P | 3 | 1 | 3 | 1 | 3 | 5 | 15 | 5 | 15
B6 | Forecast of Schedule at Completion | P | 3 | 1 | 3 | 1 | 3 | 5 | 15 | 5 | 15
B7 | Schedule for Next Phase Work Scope | P | 3 | 5 | 15 | 5 | 15 | 5 | 15 | 5 | 15
Subtotal Schedule Element |  |  |  |  | 42 |  | 52.5 |  | 139.5 |  | 150
C. SCOPE/TECHNICAL
C1 | Systems Engineering/System Design Descriptions | H | 3.2 | 3 | 9.5 | 4 | 12.7 | 5 | 15.9 | 5 | 15.9
C2 | Alternative Analysis | H | 3.2 | 5 | 15.9 | 5 | 15.9 | 5 | 15.9 | 5 | 15.9
C3 | Functional and Operational Requirements | H | 3.2 | 2 | 6.4 | 4 | 12.7 | 5 | 15.9 | 5 | 15.9
C4 | Design Basis (How) | H | 3.2 | 2 | 6.4 | 4 | 12.7 | 5 | 15.9 | 5 | 15.9
C5 | Design Criteria/Design Margins (How to) | P | 1.5 | 1 | 1.5 | 4 | 5.8 | 5 | 7.3 | 5 | 7.3
C6 | Technology Needs Identified | P | 1.5 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3 | 5 | 7.3
C7 | Technology Needs Demonstrated | H | 3.2 | 2 | 6.4 | 4 | 12.7 | 5 | 15.9 | 5 | 15.9
C8 | Trade-Off Optimization Studies | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3
C9 | Site Location | P | 1.5 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3 | 5 | 7.3
C10 | Plot Plan | P | 1.5 | 2 | 2.9 | 4 | 5.8 | 5 | 7.3 | 5 | 7.3
C11 | Process Flow Diagrams (PFDs) | P | 1.5 | N/A | 0 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C12 | Natural Phenomena | P | 1.5 | 2 | 2.9 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3
C13 | Layout Drawings and Equipment List | P | 1.5 | N/A | 0 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C14 | Piping & Instrumentation Diagrams (P&ID) | H | 3.2 | N/A | 0 | 3 | 9.5 | 4 | 12.7 | 5 | 15.9
C15 | Mechanical (Piping) | P | 1.5 | N/A | 0 | 1 | 1.5 | 2 | 2.9 | 5 | 7.3
C16 | Instrument & Electrical | P | 1.5 | N/A | 0 | 1 | 1.5 | 2 | 2.9 | 5 | 7.3
C17 | Site Characterization (Including Surveys & Soil Tests) | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3
C18 | Waste Characterization and Disposition | H | 3.2 | 1 | 3.2 | 3 | 9.5 | 5 | 15.9 | 5 | 15.9
C19 | Pollution Prevention & Waste Minimization | P | 1.5 | 2 | 2.9 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C20 | Waste Storage, Packaging and Transportation | H | 3.2 | 2 | 6.4 | 3 | 9.5 | 5 | 15.9 | 5 | 15.9
C21 | NEPA Documentation | H | 3.2 | 2 | 6.4 | 4 | 12.7 | 5 | 15.9 | 5 | 15.9
C22 | Long Lead/Critical Equipment & Material List | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C23 | Design Completion | P | 1.5 | N/A | 0 | 1 | 1.5 | 2 | 2.9 | 5 | 7.3
C24 | Design Reviews | P | 1.5 | N/A | 0 | 5 | 7.3 | 5 | 7.3 | 5 | 7.3
C25 | Interface Planning and Control | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C26 | Operating, Maintenance & Reliability (OMR) Concepts | P | 1.5 | 2 | 2.9 | 4 | 5.8 | 5 | 7.3 | 5 | 7.3
C27 | Safeguards and Security | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C28 | Heat and Material Balances | P | 1.5 | N/A | 0 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3
C29 | Reliability, Availability, Maintainability & Inspectability (RAMI) Analysis | P | 1.5 | N/A | 0 | 3 | 4.4 | 4 | 5.8 | 5 | 7.3
C30 | Materials Loading/Unloading/Staging | P | 1.5 | 1 | 1.5 | 2 | 2.9 | 4 | 5.8 | 5 | 7.3
C31 | Constructability and Construction Planning | H | 3.2 | N/A | 0 | 2 | 6.4 | 4 | 12.7 | 5 | 15.9
C32 | Sustainable Design | P | 1.5 | 1 | 1.5 | 3 | 4.4 | 5 | 7.3 | 5 | 7.3
C33 | Transition and Startup Planning | H | 3.2 | N/A | 0 | 3 | 9.5 | 4 | 12.7 | 5 | 15.9
C34 | Operations Plans and Procedures | P | 1.5 | N/A | 0 | 1 | 1.5 | 3 | 4.4 | 5 | 7.3
C35 | Civil, Structural and Architectural | P | 1.5 | 1 | 1.5 | 2 | 2.9 | 3 | 4.4 | 5 | 7.3
Subtotal Scope/Technical Element |  |  |  |  | 94.5 |  | 226.2 |  | 309.5 |  | 350.1
D. MANAGEMENT PLANNING AND CONTROL
D1 | Mission Need Statement | H | 2.2 | 5 | 11.1 | 5 | 11.1 | 5 | 11.1 | 5 | 11.1
D2 | Acquisition Strategy Plan | H | 2.2 | 3 | 6.7 | 5 | 11.1 | 5 | 11.1 | 5 | 11.1
D3 | Key Project Assumptions | P | 1.7 | 3 | 5 | 4 | 6.7 | 5 | 8.3 | 5 | 8.3
D4 | Project Execution Plan (PEP) | H | 2.2 | 1 | 2.2 | 3 | 6.7 | 5 | 11.1 | 5 | 11.1
D5 | Integrated Project Team (IPT) and Charter | P | 1.7 | 2 | 3.3 | 3 | 5 | 5 | 8.3 | 5 | 8.3
D6 | Conceptual Design Report (CDR) | H | 2.2 | N/A | 0 | 5 | 11.1 | 5 | 11.1 | 5 | 11.1
D7 | Baseline Change Control | H | 2.2 | 1 | 2.2 | 4 | 8.9 | 5 | 11.1 | 5 | 11.1
D8 | Project Control | P | 1.7 | N/A | 0 | 3 | 5 | 5 | 8.3 | 5 | 8.3
D9 | Project Work Breakdown Structure (WBS) | P | 1.7 | 1 | 1.7 | 4 | 6.7 | 5 | 8.3 | 5 | 8.3
D10 | Resources Required (People/Material) for Next Phase | P | 1.7 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3
D11 | Configuration Management | H | 2.2 | 1 | 2.2 | 3 | 6.7 | 5 | 11.1 | 5 | 11.1
D12 | Project Risk Management Plan/Assessment | H | 2.2 | 2 | 4.4 | 3 | 6.7 | 5 | 11.1 | 5 | 11.1
D13 | Quality Assurance Program | H | 2.2 | 1 | 2.2 | 4 | 8.9 | 5 | 11.1 | 5 | 11.1
D14 | Value Engineering | P | 1.7 | 1 | 1.7 | 3 | 5 | 5 | 8.3 | 5 | 8.3
D15 | Procurement Packages | P | 1.7 | N/A | 0 | 1 | 1.7 | 2 | 3.3 | 5 | 8.3
D16 | Project Acquisition Process | P | 1.7 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3
D17 | Integrated Regulatory Oversight Program | P | 1.7 | 2 | 3.3 | 4 | 6.7 | 5 | 8.3 | 5 | 8.3
D18 | Inter-Site and On-Site Coordination | P | 1.7 | 2 | 3.3 | 3 | 5 | 5 | 8.3 | 5 | 8.3
D19 | Stakeholder Program | H | 2.2 | 2 | 4.4 | 4 | 8.9 | 5 | 11.1 | 5 | 11.1
D20 | Funds Management | P | 1.7 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3
D21 | Reviews/Assessments | P | 1.7 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3 | 5 | 8.3
Subtotal Management Planning and Control Element |  |  |  |  | 86.9 |  | 155.1 |  | 194.5 |  | 199.5
E. SAFETY
E1 | Hazard Analysis/Safety Documentation | P | 5 | 2 | 10 | 4 | 20 | 5 | 25 | 5 | 25
E2 | Integrated Safeguards and Security Planning | P | 5 | 1 | 5 | 4 | 20 | 4 | 20 | 5 | 25
E3 | ES&H Management Planning (Including ISM) | H | 15 | 2 | 30 | 4 | 60 | 4 | 60 | 5 | 75
E4 | Emergency Preparedness | P | 5 | 1 | 5 | 2 | 10 | 4 | 20 | 5 | 25
Subtotal Safety Element |  |  |  |  | 50 |  | 110 |  | 125 |  | 150
TOTAL |  |  |  |  | 309.4 |  | 606.8 |  | 902 |  | 999.6