## Cur Perf
Current Performance on Projects with Approved Baselines
Program | PARSID | DOE Project Number | Project Name | RYG Overall | Current Critical Decision | Original Approved Cost ($) | Original Completion Date | Rebase | Rebaselined Project Cost ($) | Rebaselined Completion Date | Site
EM | 390 | 01-D-416 | Waste Treatment and Immobilization Plant | Red | CD4A | 5781000000 | 2011-07-31 | 3 | 18524000000 | 2027-09-30 | HFO | RYG-Monthly Overall Assessment
EM | 1021 | 14-D-403 | Outfall 200 Mercury Treatment Facility | Red | CD3 | 224000000 | 2025-09-30 |  |  |  | Oak Ridge | Red | Project is expected to breach its performance baseline cost, schedule, or scope.
EM | 1090 | 20-U-401 | On-Site Waste Disposal Facility - Infrastructure Construction | Green | CD3 | 373000000 | 2027-09-30 |  |  |  | Portsmouth | Yellow | Project is at risk of breaching its performance baseline cost, schedule, or scope.
EM | 1133 | 20-D-401 | Saltstone Disposal Unit #10, 11, 12 | Green | CD3 | 496000000 | 2030-07-08 |  |  |  | SRS | Green | Project is expected to meet its performance baseline cost, schedule, or scope.
EM | 1216 |  | X-333 Process Building Demolition Project | Green | CD3 | 537200000 | 2033-06-30 |  |  |  | Portsmouth
EM | 1239 | 24-D-401 | Environmental Restoration Disposal Facility | Green | CD3 | 95300000 | 2028-09-30 |  |  |  | HFO
EM | 1262 | OR-0041.IFDP.C1 | Alpha-2 Complex Demolition | Green | CD3 | 92000000 | 2028-10-31 |  |  |  | Oak Ridge
EM | 1278 | 22-D-404 | Additional ICDF Landfill Disposal Cell and Evaporation Ponds Project Subproject 2 | Green | CD3 | 54300000 | 2027-05-31 |  |  |  | INL