ESPC ESA Toolkit Checklist

| Phase and Recommended Steps |  |  |  | Responsible Team Member(s) |  | Notes |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Forming a Strong Project Team |  |  |  |  |  |  |  |
|  |  | Hold kickoff meeting. |  | Energy champion |  |  |  |
|  |  | Develop charter and/or project plan. |  | Energy champion |  |  |  |
| Phase 2: Project Validation |  |  |  |  |  |  |  |
|  |  | Ensure that third party power sales are allowed in state and the utility service territory. |  | Energy champion, Legal |  |  |  |
|  |  | Check on applicable agency policies. |  | Energy champion, Legal |  |  |  |
|  |  | Review OMB requirements. |  | Energy champion, Legal |  |  |  |
|  |  | Review ESPC savings and other requirements. |  | Energy champion, Contracting officer, Legal |  |  |  |
|  |  | Review IRS Revenue Procedure 2017-19. |  | Contracting officer, Legal, Energy champion |  |  |  |
|  |  | Ensure that the competitive electric contract does not have provisions that will impact project viability. |  | Energy champion |  |  |  |
|  |  | Complete project cost effectiveness analysis. |  | Energy champion |  |  |  |
|  |  | Determine optimal solar PV project size. |  | Energy champion |  |  |  |
|  |  | Ensure solar project is compatible with mission and site plans. |  | Energy champion, Leadership |  |  |  |
|  |  | Determine land/building ownership and obtain approvals. |  | Real property, Leadership |  |  |  |
|  |  | Obtain approval for project from entity that pays the utility bills. |  | Energy champion, Leadership |  |  |  |
|  |  | Coordinate with tenants about solar project. |  | Energy champion, Leadership |  |  |  |
|  |  | Obtain agency approval for project at required levels. |  | Energy champion, Leadership |  |  |  |
|  |  | Set up meeting with utility to discuss the Utility Coordination Topics described in Phase 2, Project Validation. |  | Energy champion |  |  |  |
|  |  | Determine available incentives. |  | Energy champion |  |  |  |
|  |  | Determine applicable policies such as net metering. |  | Energy champion |  |  |  |
|  |  | Address the question: Is there a possible tariff change and/or standby charge? |  | Energy champion |  |  |  |
|  |  | Investigate interconnection processes and requirements. |  | Energy champion, Electrical engineer |  |  |  |
|  |  | Determine who signs the interconnection agreement (ICA). |  | Energy champion |  |  |  |
|  |  | Conduct legal review of the ICA. |  | Energy champion, Legal |  |  |  |
|  |  | Discuss Site Access Agreement options with real property staff. |  | Energy champion, Real property |  |  |  |
|  |  | Consult with electrical engineer – discuss electrical considerations and develop solar project electrical connection plan. |  | Energy champion, Electrical engineer |  |  |  |
|  |  | Discuss NEPA, stormwater management, erosion/sediment control and other environmental requirements with environmental staff or other appropriate staff. |  | Energy champion, Environmental |  |  |  |
|  |  | Determine applicable National Historic Preservation Act (NHPA) and other historic preservation requirements. |  | Environmental |  |  |  |
|  |  | Check agency glare policy. |  | Energy champion |  |  |  |
|  |  | Complete glare study if necessary. |  | Energy champion |  |  |  |
|  |  | Ensure agency and/or FAA review of glare study. |  | Energy champion |  |  |  |
|  |  | Determine applicable construction and operating permits. |  | Energy champion, Site operations |  |  |  |
| Phase 3: Acquisition Planning |  |  |  |  |  |  |  |
|  |  | Discuss small business requirements with agency small business staff. |  | Contracting officer, Legal |  |  |  |
|  |  | Conduct small business market research. |  | Contracting officer, Energy champion |  |  |  |
|  |  | Complete necessary small business paperwork and obtain all approvals. |  | Contracting officer |  |  |  |
|  |  | Finalize acquisition plan. |  | Contracting officer |  |  |  |
| Phase 4: RFP Development |  |  |  |  |  |  |  |
|  |  | Complete NEPA. |  | Environmental |  |  |  |
|  |  | Review contractual issues. |  | Contracting officer |  |  |  |
|  |  | Make decisions on various contractual issues: |  | Contracting officer |  |  |  |
|  |  | Termination for convenience clause(s). |  | Contracting officer |  |  |  |
|  |  | Buy American Act. |  | Contracting officer |  |  |  |
|  |  | Davis Bacon and Services Contract Act. |  | Contracting officer |  |  |  |
|  |  | Fair market value purchase and ESCO’s reserve account requirement language. |  | Contracting officer |  |  |  |
|  |  | Develop source selection plan (may also be done in Phase 3). |  | Contracting officer |  |  |  |
|  |  | Discuss project with site security staff. |  | Energy champion |  |  |  |
|  |  | Discuss project with safety staff. |  | Energy champion |  |  |  |
|  |  | Discuss cybersecurity requirements. |  | Energy champion, Computer services |  |  |  |
|  |  | Assemble RFP. |  | Contracting officer |  |  |  |
|  |  | Compile exhibits. |  | Energy champion |  |  |  |
|  |  | Develop Site Access Agreement. |  | Contracting officer, Real property, legal |  |  |  |
|  |  | Obtain final RFP, Site Access Agreement, and Source Selection Plan approvals. |  | Contracting officer, Legal, Real property |  |  |  |
| Phase 5: Procurement |  |  |  |  |  |  |  |
|  |  | Plan pre-proposal conference/site visits. |  | Contracting officer |  |  |  |
|  |  | Issue solicitation. |  | Contracting officer |  |  |  |
|  |  | Hold pre-proposal conference/site visits. |  | Contracting officer, Energy champion |  |  |  |
|  |  | Post amendments (as needed). |  | Contracting officer |  |  |  |
|  |  | Post Q&A document. |  | Contracting officer, Energy champion |  |  |  |
| Phase 6: Proposal Evaluation and Contract Award |  |  |  |  |  |  |  |
|  |  | Evaluate proposals. |  | Evaluation team |  |  |  |
|  |  | Conduct negotiations, if needed. |  | Contracting officer |  |  |  |
|  |  | Obtain all required agency approvals. |  | Contracting officer |  |  |  |
|  |  | Review congressional notification requirements for your agency. |  | Contracting officer |  |  |  |
|  |  | Award contract and notify other offerors |  | Contracting officer |  |  |  |
| Phase 7: Construction and Performance Period |  |  |  |  |  |  |  |
|  |  | Conduct a post award orientation conference. |  | Energy champion |  |  |  |
|  |  | Obtain required plans from contractor. |  | Contracting officer |  |  |  |
|  |  | Review PV system design. |  | Energy champion |  |  |  |
|  |  | Confirm interconnection requirements & submit application. |  | Energy champion |  |  |  |
|  |  | Complete project inspection, commissioning and acceptance based on agency requirements. |  | Energy champion |  |  |  |
|  |  | Obtain utility interconnection approval. |  | Energy champion |  |  |  |
|  |  | Sign interconnection agreement. |  | Contracting officer |  |  |  |
|  |  | Pay invoices. |  | Finance/Accounting |  |  |  |
|  |  | Review and approve annual M&V report. |  | Contracting officer |  |  |  |
|  |  | Conduct periodic FMV re-evaluations and adjust the government’s reserve account payment (if needed). |  | Contracting officer, Energy champion |  |  |  |
|  |  | Request official solar project FMV assessment. |  | Contracting officer |  |  |  |
|  |  | Purchase equipment at FMV. |  | Contracting officer |  |  |  |
|  |  | ESCO should apply remaining reserve account funds (if any) to remaining ESPC balance. |  | Contracting officer |  |  |  |
|  |  | Close out the contract. |  | Contracting officer |  |  |  |

A NOITA is an optional step before contract award. See Process Diagram, Phase 6 footnote.