## Acronyms
Acronym | Full text
AT | Acquisition Team
CO | Contracting Officer
CPARS | Contractor Performance Assessment Reporting System
CUI | Controlled Unclassified Information
DOE | Department of Energy
ECM | Energy Conservation Measure
ESCO | Energy Service Company
FPE | Federal Project Executive
FY | Fiscal Year
GFO | Golden Field Office
HQ | Headquarters
IDIQ | Indefinite Delivery Indefinite Quantity
IGA | Investment Grade Audit
M&V | Measurement and Verification
NOITA | Notice of Intent to Award
NOO | Notice of Opportunity
OMRR | Operations, Maintenance, Repair, and Replacement
PA | Preliminary Assessment
PF | Project Facilitator
RRPM | Risk, Responsibility, and Performance Matrix
TO | Task Order

## ESPC Schedule with PA
Project Name: | Jones Laboratories
Date of Last Update: | 2024-02-15
[5 empty] | Estimated | Actual
Stand alone tasks - not critical path |  |  | Time from Phase 1 to TO Award: |  | 20 | 0
Tasks that must be done before the following task - Critical Path
Key Milestones that require stakeholder approval and Contracting Officer action
Activity | Timeline |  | Completion Dates |  |  |  | ESCO | Gov't Site/Agency | FEMP Support | PF | GFO
| Calendar Days, Working Days1 |  | Estimated Start | Actual | Estimated End | Actual End
Start Date |  |  | 02/15/2024 |  | 2025-09-22
Phase 1 - Project Planning | 30-60 | Total Elapsed Days
Contact FPE to assist with training, project planning, and latest FEMP Guidance Documents | 3 | 5 | 02/15/2024 |  | 2024-02-20 |  |  | Outreach | X
Review FEMP Best Practices Document and FAQs | 2 | 11 | 2024-02-22 |  | 2024-02-26 |  |  | X | X
Review the DOE guidance "Federal ESPC Process Phase 1: Acquisition Planning" | 1 | 11 | 2024-02-23 |  | 2024-02-26 |  |  | X | X
Establish Acquisition Team (AT) and develop acquisition plan | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X | Support
Gather preliminary data for NOO - Utility spend (1 year), utility usage, building square footage, age, type. | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X
Create Milestone Plan | 3 | 15 | 2024-02-27 |  | 2024-03-01 |  |  | X | Support
AT develops NOO & source selection plan | 10 | 35 | 2024-03-07 |  | 2024-03-21 |  |  | X | Support
Site works with FPE to request a Project Facilitator (PF) | 5 | 35 | 2024-03-14 |  | 2024-03-21 |  |  | X | X
Golden Field Office (GFO) begins PF procurement | 60 | 105 | 2024-03-07 |  | 2024-05-30 |  |  | X | Support
Provide written notification to DOE IDIQ CO of intent to issue NOO | 3 | 29 | 2024-03-12 |  | 2024-03-15 |  |  | X | Support
Contracting Officer (CO) issues NOO to sam.gov and/or other public procurement websites | 22 | 57 | 2024-03-13 |  | 2024-04-12 |  |  | X | Support
Coordinate ESPC Training for project team | 5 | 40 | 2024-03-19 |  | 2024-03-26 |  |  | X | X
Phase 2 - Selecting the ESCO - preliminary | 45
ESCOs submits Expression of Interest (EOI) responses to NOO | 25 | 62 | 2024-03-13 |  | 2024-04-17 |  | X
Acquisition team down selection to multiple ESCOs | 20 | 90 | 2024-04-17 |  | 2024-05-15 |  |  | X |  | X
ESCO down selection notification & notice to proceed with finalists | 1 | 91 | 2024-05-15 |  | 2024-05-16 |  |  | X
Phase 2 - Selecting final ESCO
ESCOs submit further info and/or respond to oral interviews | 10 | 105 | 2024-05-16 |  | 2024-05-30 |  | X
Acquisition Team reviews further information and down selects to one ESCO for PA | 10 | 119 | 2024-05-30 |  | 2024-06-13 |  |  | X |  | X
CO sends down selection notice to unsuccessful ESCO offerors | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X
CO issues Successful Offer Letter to selected ESCO for Preliminary Assessment (PA) | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X |  |  | Receives notice from site/agency CO
ESCO notifies CO of intent to proceed to PA | 1 | 123 | 2024-06-14 |  | 2024-06-17 |  | X
Phase 2 - ESCO Performs Preliminary Assessment | 60
Begin contractor site access and clearance process (if required) | 5 | 130 | 2024-06-17 |  | 2024-06-24 |  | X | X
Ensure Government escorts are available for site visits (if required) | 5 | 130 | 2024-06-17 |  | 2024-06-24 |  |  | X
Preliminary Assessment (PA) kickoff meeting with ESCO, PF, FPE | 1 | 132 | 2024-06-25 |  | 2024-06-26 |  | X | X | X | X
Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 5 | 139 | 2024-06-26 |  | 2024-07-03 |  | X
Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X
Weekly or Biweekly progress meetings | [6 empty] | X | X | X | X
Site receives PA | 45 | 202 | 2024-07-03 |  | 2024-09-04 |  | X
AT convenes and reviews PA results | 5 | 209 | 2024-09-04 |  | 2024-09-11 |  |  | X | Support | X
PA Comments (from gov't) | 20 | 237 | 2024-09-11 |  | 2024-10-09 |  |  | X | X | X
PA Comment Response (from ESCO) | 15 | 258 | 2024-10-09 |  | 2024-10-30 |  | X
CO issues NOITA & Draft TO RFP | 5 | 265 | 2024-10-30 |  | 2024-11-06 |  |  | X
Phase 3 - Investment Grade Audit | 175
IGA Kickoff Meeting | 1 | 301 | 2024-12-11 |  | 2024-12-12 |  | X | X | X | X
Issue draft TORFP | 1 | 278 | 2024-11-18 |  | 2024-11-19 |  | X | X
Begin contractor site access and clearance process (if required) | 5 | 272 | 2024-11-06 |  | 2024-11-13 |  |  | X
Ensure Government escorts are available for site visits (if required) | 5 | 272 | 2024-11-06 |  | 2024-11-13 |  |  | X
Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 10 | 315 | 2024-12-12 |  | 2024-12-26 |  | X
Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X | Support
Weekly or Biweekly progress meetings | [6 empty] | X | X | Support | X
ESCO Milestone project reviews, as needed. Concurrence on RRPM items in DOE IDIQ contract. | [6 empty] | X | Support
ECM Scope Workshop | 1 |  | 2025-03-06 |  | 2025-03-07 |  | X | X | S | X
M&V Workshop | 1 |  | 2025-04-17 |  | 2025-04-18 |  | X | X | S | X
OMRR Workshop | 1 |  | 2025-03-19 |  | 2025-03-20 |  | X | X | S | X
ESCO completes IGA and submits | 100 | 455 | 2024-12-26 |  | 2025-05-15 |  | X
Government review and comments | 25 | 490 | 2025-05-15 |  | 2025-06-19 |  |  | X |  | X
ESCO Comment response | 25 | 525 | 2025-06-19 |  | 2025-07-24 |  | X
ESCO revisions to comments, issues Final Proposal | 10 | 539 | 2025-07-24 |  | 2025-08-07 |  | X
Phase 3: Negotiation and Award | 30
AT / CO requests and obtains executive approval for Final Proposal | 10 | 553 | 2025-08-07 |  | 2025-08-21 |  |  | X
DOE IDIQ CO Review of Final Proposal | 10 | 504 | 2025-06-19 |  | 2025-07-03 |  |  | X |  |  | X
Congressional Notification (If required) (31 calendar days) | 23 | 572 | 2025-08-07 |  | 2025-09-09 |  |  | X
Project Negotiations | 10 | 567 | 2025-08-21 |  | 2025-09-04 |  | X | X
Finalize TO Award documents, Final Task Order schedules (includes all reviews and approvals) | 5 | 574 | 2025-09-04 |  | 2025-09-11 |  | X | X |  | X
Lock Interest Rate | 5 | 581 | 2025-09-11 |  | 2025-09-18 |  | X | Direct ESCO
ESCO provides revised Task Order Schedules with locked interest rate | 1 | 582 | 2025-09-18 |  | 2025-09-19 |  |  | X
Sign Task Order | 1 | 585 | 2025-09-19 |  | 2025-09-22 |  | X | X
1. Days in this column are not additive. Some occur simultaneously. Number of day are approximate and suggested dates for expedited DOE ESPC IDIQ.
Formulas:
Estimated End = WORKDAY([Completion Dates],[Timeline])
Completion Dates = WORKDAY([Estimated End, row above],[Timeline])
Completion Dates = WORKDAY([Completion Dates, row above],[Timeline])

## ESPC Schedule without PA
| Project Name: | Jones Laboratories
| Date of Last Update: | 2024-02-15
[6 empty] | Estimated | Actual
| Stand alone tasks - not critical path |  |  | Time from Phase 1 to TO Award: |  | 15 | 0
Tasks that must be done before the following task - Critical Path
Key Milestones that require stakeholder approval and Contracting Officer action
| Activity | Timeline |  | Completion Dates |  |  |  | ESCO | Gov't Site/Agency | FEMP Support | PF | GFO
|  | Calendar Days, Working Days1 |  | Estimated Start | Actual | Estimated End | Actual End
| Start Date |  |  | 02/15/2024 |  | 2025-04-30
| Phase 1 - Project Planning | 30-60 | Total Elapsed Days
1 | Contact FPE to assist with training, project planning, and latest FEMP Guidance Documents | 3 | 5 | 02/15/2024 |  | 2024-02-20 |  |  | Outreach | X
2 | Review FEMP Best Practices Document and FAQs | 2 | 11 | 2024-02-22 |  | 2024-02-26 |  |  | X | X
3 | Review the DOE guidance "Federal ESPC Process Phase 1: Acquisition Planning" | 1 | 11 | 2024-02-23 |  | 2024-02-26 |  |  | X | X
4 | Establish Acquisition Team (AT) and develop acquisition plan | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X | S
5 | Gather preliminary data for NOO - Utility spend (1 year), utility usage, building square footage, age, type. | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X
6 | Create Milestone Plan | 3 | 15 | 2024-02-27 |  | 2024-03-01 |  |  | X | S
7 | AT develops NOO & source selection plan | 10 | 35 | 2024-03-07 |  | 2024-03-21 |  |  | X | S
8 | Site works with FPE to request a Project Facilitator (PF) | 5 | 35 | 2024-03-14 |  | 2024-03-21 |  |  | X | X
9 | Golden Field Office (GFO) begins PF procurement | 60 | 105 | 2024-03-07 |  | 2024-05-30 |  |  | X | S
10 | Provide written notification to DOE IDIQ CO of intent to issue NOO | 3 | 29 | 2024-03-12 |  | 2024-03-15 |  |  | X | S
11 | Contracting Officer (CO) issues NOO to sam.gov and/or other public procurement websites | 22 | 57 | 2024-03-13 |  | 2024-04-12 |  |  | X | S
12 | Coordinate ESPC Training for project team | 5 | 40 | 2024-03-19 |  | 2024-03-26 |  |  | X | X
| Phase 2 - Selecting the ESCO - preliminary | 45
1 | ESCOs submits Expression of Interest (EOI) responses to NOO | 25 | 62 | 2024-03-13 |  | 2024-04-17 |  | X
2 | Acquisition team down selection to multiple ESCOs | 20 | 90 | 2024-04-17 |  | 2024-05-15 |  |  | X |  | X
3 | ESCO down selection notification & notice to proceed with finalists | 1 | 91 | 2024-05-15 |  | 2024-05-16 |  |  | X
Phase 2 - Selecting final ESCO
1 | ESCOs submit further info and/or respond to oral interviews | 10 | 105 | 2024-05-16 |  | 2024-05-30 |  | X
2 | Acquisition Team reviews further information and down selects to one ESCO for PA | 10 | 119 | 2024-05-30 |  | 2024-06-13 |  |  | X |  | X
3 | CO sends down selection notice to unsuccessful ESCO offerors | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X
4 | CO issues Notice of Intent to Award to ESCO finalist | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X |  |  | Receives notice from site/agency CO
5 | ESCO notifies CO of intent to proceed to IGA | 1 | 123 | 2024-06-14 |  | 2024-06-17 |  | X
| Phase 2 - ESCO Performs Preliminary Assessment | N/A
Begin contractor site access and clearance process (if required)
Ensure Government escorts are available for site visits.
Preliminary Assessment (PA) kickoff meeting with ESCO, PF, FPE
Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs)
| Requests for Information - ESCO issues and site responds. | Ongoing
Weekly or Biweekly progress meetings
Site receives PA
AT convenes and reviews PA results
CO issues NOITA & Draft TO RFP
| Phase 3 - Investment Grade Audit | 205
1 | IGA Kickoff Meeting | 1 | 159 | 2024-07-22 |  | 2024-07-23 |  | X | X | X | X
2 | Issue draft TORFP | 1 | 134 | 2024-06-27 |  | 2024-06-28 |  |  | X
3 | Begin contractor site access and clearance process (if required) | 1 | 134 | 2024-06-27 |  | 2024-06-28 |  | X | X
4 | Ensure Government escorts are available for site visits (if required) | 5 | 130 | 2024-06-17 |  | 2024-06-24 |  |  | X
5 | Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 10 | 173 | 2024-07-23 |  | 2024-08-06 |  | X
6 | Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X | S
7 | Weekly or Biweekly progress meetings | [6 empty] | X | X | S | X
8 | ESCO Milestone project reviews, as needed. Concurrence on RRPM items in DOE IDIQ contract. | [6 empty] | X | S
9 | ECM Scope Workshop | 1 |  | 2024-11-05 |  | 2024-11-06 |  | X | X | S | X
10 | M&V Workshop | 1 |  | 2024-12-03 |  | 2024-12-04 |  | X | X | S | X
11 | OMRR Workshop | 1 |  | 2024-12-03 |  | 2024-12-04 |  | X | X | S | X
12 | ESCO completes IGA and submits | 120 | 341 | 2024-08-06 |  | 2025-01-21 |  | X
13 | Government review and comments | 15 | 362 | 2025-01-21 |  | 2025-02-11 |  |  | X |  | X
14 | ESCO Comment response | 15 | 383 | 2025-02-11 |  | 2025-03-04 |  | X
15 | ESCO revisions to comments, issues Final Proposal | 10 | 397 | 2025-03-04 |  | 2025-03-18 |  | X
| Phase 3: Negotiation and Award | 30
1 | AT / CO requests and obtains executive approval for final proposal | 10 | 411 | 2025-03-18 |  | 2025-04-01 |  |  | X
2 | DOE IDIQ CO Review of Final Proposal | 10 | 376 | 2025-02-11 |  | 2025-02-25 | [5 empty] | X
3 | Congressional Notification (If required) (31 calendar days) | 24 | 431 | 2025-03-18 |  | 2025-04-21 |  |  | X
4 | Project Negotiations | 10 | 425 | 2025-04-01 |  | 2025-04-15 |  | X | X
5 | Finalize TO Award documents, Final Task Order schedules (includes all reviews and approvals) | 5 | 432 | 2025-04-15 |  | 2025-04-22 |  | X | X |  | X
6 | Lock Interest Rate | 5 | 439 | 2025-04-22 |  | 2025-04-29 |  | X | Direct ESCO
7 | ESCO provides revised Task Order Schedules with locked interest rate | 1 | 533 | 2025-07-31 |  | 2025-08-01 |  |  | X
8 | Sign Task Order | 1 | 440 | 2025-04-29 |  | 2025-04-30 |  | X | X
1. Days in this column are not additive. Some occur simultaneously. Number of day are approximate and suggested dates for expedited DOE ESPC IDIQ.
Formulas:
Estimated End = WORKDAY([Completion Dates],[Timeline])
Completion Dates = WORKDAY([Estimated End, row above],[Timeline])
Completion Dates = WORKDAY([Completion Dates, row above],[Timeline])
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove?