## Slide 1
Dave Fong, Courtney Allen, Carla Jordan
(contributions by Pamela DiVito)
Sandia National Laboratories
August 13, 2026
Journey of a Cost Estimate – W87-1 Modification Program
SAND2026-24748PE P

## Slide 2
1. Program & Replan Context
Background on W87-1 Mod Program timeline, lifecycle phases, and key transition from WDCR to the 2025 Replan.
2. Peer Review Execution
Peer review framework replacing formal ICER, critical focus areas across technical/programmatic domains, and key results.
3. Risk, Uncertainty & SCURA
Early integration of risk management, Schedule and Cost Uncertainty Analysis (SCURA) timeline, and quantitative results.
4. Data & Future Roadmap
Simplifying complex P6 data, LOE control accounts, GAO cost credibility standards, and path to FY27 Baseline Cost Report (BCR).
Presentation Outline

## Slide 3
2022 WDCR Phase
Initial Weapon Design Cost Report estimate established.
2025 Replan
Comprehensive scope, schedule, and cost alignment.
2026-2027
Baseline Cost Report
Formal BCR submittal for Phase 6.4 entry.
2028-2033
Future Replans/BCR updates
Product Lifecycle Review Timeline

## Slide 4
Schedule & Logic Alignment
Cost, FYNSP Target Realism, Risk
LOE Percentages: Establish clear Level of Effort baselines across all key stakeholders.
Schedule Constraints: Define explicit assumptions early (fixed target dates vs. range).
Joint Milestones: Enforce mutually agreed-upon due dates between M&O, NNSA, and DoD Flight Tests.
P6 Pipeline: Develop staff training pipeline to sustain specialized Primavera P6 expertise.
Early Target Setting: Establish total program ROM/Target early to ensure cost reasonableness.
FYNSP Constraints: Directly factor in Future Years Nuclear Security Program funding limits.
Integrated Core Team: Maintain unified leadership spanning Cost, Schedule, and Risk/SCURA.
Early Peer Reviews: Shift peer reviews upstream rather than at final deliverable stages.
Lessons Learned: WDCR to Replan
SCURA: Improve quantification of cost and schedule impacts in risk
Staff experience: Grow knowledge base across cost and risk

## Slide 5
Comprehensive Alternative to ICER
Replaced the formal PMO Independent Cost Estimate Review (ICER) with a proactive internal peer review process to ensure readiness and technical rigor.
Review Architecture
Primary Review Objective:
Foster successful replan through early identification of programmatic and technical gaps. Positioned as collaborative assistance rather than an audit.
Benchmark Lessons: Analyzed peer review outcomes from preceding weapon programs.
SME Pairing: Paired technical Subject Matter Experts directly with Project Managers.
Targeted Focus: Defined clear criteria spanning technical scope, cost, and schedule elements.
Structured Kickoff: Conducted aligned kickoff sessions for review teams.
Replan Peer Review Strategy

## Slide 6
Sandia National Laboratories
Programmatic Costs
Technical Readiness
Schedule Logic
Estimate Realism
FY26 target alignment
Total Labor Equivalents (TLEs)
Procurement commit timing
Air Force vs. NNSA sharing
Critical path vs challenges
PRT hardware requirements
Design description fit
Technical knowledge gaps
Activity durations & logic
Key milestone alignment
Target date feasibility
Critical path validity
Baseline variance analysis
LOE re-assessment
Outyear impact evaluation
Historical actuals check
Peer Review Process & Focus Areas
Initial Evaluation
Kickoff
Technical & Programmatic
Reviewers Alignment with Feedback
Peer Review Feedback with Applicable Team
Follow-up on Progress Against Actions
Leadership Review/ ICER Summary Report
Process Flow:

## Slide 7
Peer Review Attributes

## Slide 8
Successful Practices
Key Areas for Refinement
Fiscal Year Assessment Tools: Newly created tools to evaluate estimates by FY were highly praised.
Systems-Level Iterations: Follow-up reviews with Systems and PMO successfully aligned costs to targets.
Historical Actuals Integration: Program actuals to date provided essential sanity checks.
Outyear Targets: Target guidance was limited to Year 1, leading teams to assume unconstrained outyear growth.
Communicating Limits: Total cost increase expectations were not conveyed early enough by management.
Overly High Ramp Down: Team ramp-down estimates were too conservative and required realistic recalibration.
Peer Review Results
Structured Guidance & Lead Designation: Kickoff meetings require granular instructions. Teams lacked designated review leads, resulting in varying and inconsistent reviews
Action Item Verification Loop: While initial timelines were clear, follow-up procedures to verify that teams addressed corrective actions were undefined and infrequently validated.
SME Fit & Management Reinforcement: SME selection must prioritize technical expertise over availability. Active management enforcement of review standards is vital for consistent documentation.
Actionable Feedback: Many good observations, recommendations, and actions were identified for scope, schedule, and cost

## Slide 9
Lessons Learned: Risk & SCURA Integration
Early Integration of Risk: Staffing changes throughout WDCR; Risk not integrated with other programmatic areas
Schedule and Cost Uncertainty Training: Lack of experience and limited training
Quality of SCURA Inputs: Dry run SCURA timed too late to address input data concerns

## Slide 10
Early Integration Improvements
Unlike the WDCR process, the Risk Lead was fully embedded from day one of the Replan effort:
Targeted Training & Coaching
Addressed past training deficits with two comprehensive program-wide uncertainty workshops and individual engagement:
Uncertainty coding integrated into schedule timelines.
Internal SCURAs planned & pre-approved by leadership.
Monthly risk/uncertainty updates at check-ins.
Demonstrated how uncertainty codes affect single-point estimates.
Held 1-on-1 risk/uncertainty deep dives with teams.
Provided quantitative benchmarks (SPI/CPI, CEI, variance).
Risk & SCURA Integration

## Slide 11
SCURA Cycle | Timing | Target Audience | Key Output & Value Proposition
Internal SCURA 1 | Jan 2025 | L1/L2 Mgmt, Programmatic Leads | First time assessing MR since Oct 2023.
Internal SCURA 2 | Mar 2025 | L1/L2 Mgmt, Programmatic Leads | Schedules, ETCs, and uncertainty coding still in development; learned that overlay needed refinement.
Internal SCURA 3 | May 2025 | L1/L2 Mgmt, Programmatic Leads | Just before "pencils-down"; learned risk burn down was optimistic.
Interim SCURA (Required) | Jun 2025 | SNL Senior Leadership, W87-1 FPO | MR supporting peer review; addressed previous learnings.
Final SCURA (Required) | Oct 2025 | SNL Senior Leadership, W87-1 FPO | Final MR & schedule contingency recommendations.
Re-Baseline SCURA Timeline (2025)

## Slide 12
8%
Recommended Management Reserve (MR)
Resulting from rigorous iterative SCURA runs and quantitative data validation
Key Achievements
Clean Data Baseline: Successfully eliminated missing coding and missing justifications across all P6 tasks.
Effective Overlay Method: Refined risk overlay methodology through iterative test runs.
Reasonable Risk Burn Down: Reflected only approved and in-progress mitigations.
Impact: Risk & SCURA Integration

## Slide 13
Lessons Learned: Cost & Funding
Affordability against FYNSP: Constrain or at least factor in FYNSP funding targets in earl
Understand Time Phasing of Costs: Hardware (HW) commitments & costing
Understand Level of Effort (LOE) percentages: LOE levels Pre and Post FPU across program
Establish Total program Target: Cost range needed early to ensure cost reasonableness

## Slide 14
Leveraging Historical Data
Capitalized on 2.5 full years of actual execution data to inform future estimates:
Addressing Optimism Bias
Mitigated team tendencies to plan for "optimal" vs. "available" staffing:
Built custom template to "data dump" P6 schedules into Cobra.
Combined historical actuals seamlessly with future ETCs.
Enabled teams to analyze time-phased costs by expenditure category.
Conducted deep dives into labor headcount increases.
Deployed external technical reviewers to validate resource spikes.
Focused on alignment with FYNSP profile & FY26 targets.
Data Optimization & Actuals

## Slide 15
Expenditure Category | Hours (Labor) | Burdened Labor ($K) | Purchases ($K) | Travel & Chargebacks ($K) | Total EAC ($K)
Previous Baseline | Original Planned | $ --- | $ --- | $ --- | Baseline Ref
2025 Replan EAC | Recalibrated TLEs | Optimized | Phased Commits | Refined Rates | Updated Replan
Variance / Delta | Scope Extension | FYNSP Aligned | HW Schedule Shift | Efficiency Savings | Target Compliant
Simplicity Drives Results: Converting raw P6 schedule data into standardized cost categories enabled rapid executive decision-making and clear peer review validation.
Cost & Resource Phasing

## Slide 16
Previous Challenge
Level of Effort (LOE) accounts were fragmented across multiple work packages by engineer type and fiscal year, obscuring true long-term resource requirements.
Applied Solution
Re-categorized and labeled LOE inputs (e.g., SEI_Elec_Desgn, SEI_Mech_Desgn) to provide management with direct visibility into multi-year TLE trends.
LOE Account Simplification

## Slide 17
Looking Ahead to Phase 6.4 & FY27 BCR
The successful 2025 Replan positions the W87-1 program strongly to submit a defendable Baseline Cost Report (BCR) in FY27.
Continuous improvement of best practices, active change control, and close technical SME partnership will sustain cost credibility as scope evolves.
Comprehensive
Includes all direct and indirect lifecycle costs.
Well-Documented
Clear ground rules, assumptions & replicate data.
Accurate
Unbiased, stripped of overly optimistic assumptions, and continually updated.
Credible
Rigorous sensitivity, risk & uncertainty testing.
Cost Credibility & Path Forward
Our process included many iterative assessments of the cost estimate leading into the “pencils down” date and the refinement that occurs ahead of executive reviews
Previous lessons learned became the criteria we used in getting to a credible cost estimate