## Slide 1: Los Alamos National Laboratory’s Chromium Project Buckman Direct Diversion
Doug Hintze
Manager
Environmental Management Los Alamos Field Office
October 4, 2018

## Slide 2: Presentation Topics
Groundwater Setting
Where did the chromium come from and where is it now?
What is being done to address the plume?
Recent changes
Project status
What’s next?
Summary

## Slide 3: Groundwater beneath Los Alamos
~1000 feet
Cr Plume
Typical Water-Supply Well
Typical Monitoring Well

## Slide 4: Chromium in Groundwater Beneath LANL
? ? ? ? ? ?
- - - - -
Chromium (Cr) contamination in the regional aquifer is in hexavalent form
Potassium dichromate used in cooling towers at a Laboratory power plant
Up to 72,000 kg released from 1956-72 in hexavalent form [Cr(VI)]
  3 groundwater zones
  Plume is 900–1,000 feet below canyon bottom in deepest zone
  Size is approximately 1 mile x 1/2 mile x <75 feet thick
  Estimated downgradient plume edge is approximately 1/4 mile from the closest drinking water well
Potassium dichromate used in cooling towers at a Laboratory power plant
Up to 160,000 lb released from 1956-72 in hexavalent form [Cr(VI)]
Power Plant
Plume

## Slide 5: Updates to Plume Definition: CrIN-6
CrIN-6
CrIN-6
Installation of injection well CrIN-6 completed in July 2017
Concentration of Cr in CrIN-6 is ~270 ppb
  Consistent with model predictions of plume in the CrIN-6 area
Updated depiction of plume is based on CrIN-6 data and models that were consistent with CrIN-6 Cr concentration
Specific location of 50 ppb edge is uncertain.
Plume did not suddenly expand
Continued coordination with Los Alamos County to ensure protection of drinking water (PM-3)
From 2016 CrIN-6 Drilling Work Plan
Updated based on CrIN-6 Cr concentrations and model estimations
PM-3

## Slide 6: Interim Measure Technical Approach
E
E
E
I
I
I
Extract 
Treat
Inject
T
Hydraulic Control to Prevent Migration
E
I
I
E

Initial Phase
Second Phase

## Slide 7: Recent Changes to IM Approach
April 26, 2018 Submittal to NMED - Evaluation of Chromium Plume Control Interim Measure Operational Alternatives for Injection Well CrIN-6
Evaluated injection vs. extraction scenarios for CrIN-6
Primary considerations:
Establish control of plume edge
Protect PM-3
Rate of reduction of Cr downgradient (east) of CrIN-6
Conclusion:
Convert CrIN-6 to extraction well
Install additional monitoring well
June 6, 2018 NMED Approval to convert CrIN-6 to CrEX-5
Approximate location of new monitoring well
Groundwater Flow

## Slide 8: Goal of the Interim Measure
Approximation of plume edge 2-3 years after start up of full system operation of Interim Measure
Groundwater Flow

## Slide 9
Extraction, Treatment & Injection Loop
Extraction Well
Injection Well
INJECTED WATER RESULTS IN MOUNDING OF THE WATER TABLE
Contaminated groundwater is pumped from extraction wells
Groundwater is treated using a method called ion exchange
Clean water is delivered via buried thick-walled piping to injection wells
Water exits the injection wells within the aquifer
Ion Exchange Treatment Unit

## Slide 10: Modeling Results
Injection Scenarios
“pushes” contamination to the north and possibly towards PM-3
Extraction Scenarios
“captures” contamination from the north
more protective of PM-3
Scenarios evaluated included continuous extraction at CrEX-1, CrEX-2 and CrEX-3, and continuous injection at all injection wells

## Slide 11: Groundwater Modeling Animations
Insert movies here

## Slide 12: Project Status
Operated pumping and injection system for ~ 5 months in early 2017
Full-time operations along Laboratory boundary with Pueblo de San Ildefonso restarted late May 2018 and will run continuously for forseeable future
CrIN-6 reconfiguration activities July – December 2018
  Converting CrIN-6 into an extraction well (“CrEX-5”)
  Design/install infrastructure to connect to treatment system
Full system operation (inclusive of CrEX-5) expected to start in early 2019
Continue studies to evaluate final remedy

## Slide 13
Questions?