## Cost Performance Report
Task Order Title:
Task Order Number:
Period of Performance:
Monthly Cost Performance Report
| Total | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13
BCWS (Planned Monthly Budget) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Approved Budget
Engineering Communications Survey - C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-Construction Activities - E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction/Integration - F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance Testing - G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operational Testing and Evaluation - I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management - Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BCWP (Monthly Earned Value) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cumulative BCWP
Engineering Communications Survey - C |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-Construction Activities - E |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction/Integration - F |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance Testing - G |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operational Testing and Evaluation - I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management - Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Communications Survey - C |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-Construction Activities - E |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction/Integration - F |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance Testing - G |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operational Testing and Evaluation - I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management - Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACWP (Monthly Actuals) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cumulative ACWP
Engineering Communications Survey - C |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-Construction Activities - E |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction/Integration - F |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance Testing - G |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operational Testing and Evaluation - I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management - Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Variance (BCWP-ACWP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Communications Survey - C |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-Construction Activities - E |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction/Integration - F |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance Testing - G |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operational Testing and Evaluation - I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management - Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Comment Required? (If Yes, Click Link)
Cumulative Cost Performance Report
|  | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13
Cumulative BCWS (Planned Monthly Budget) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Communications Survey - C |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
Pre-Construction Activities - E |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
Construction/Integration - F |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
Acceptance Testing - G |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
Operational Testing and Evaluation - I |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
Project Management - Z |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0
BCWP (Cumulative Earned Value) |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Engineering Communications Survey - C |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Pre-Construction Activities - E |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Construction/Integration - F |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Acceptance Testing - G |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Operational Testing and Evaluation - I |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Project Management - Z |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
ACWP (Cumulative Actuals) | 0 | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Engineering Communications Survey - C |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Pre-Construction Activities - E |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Construction/Integration - F |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Acceptance Testing - G |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Operational Testing and Evaluation - I |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Project Management - Z |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-02: 0; 2024-01-02: 0; 2024-02-02: 0; 2024-03-04: 0; 2024-04-04: 0; 2024-05-05: 0; 2024-06-05: 0; 2024-07-06: 0; 2024-08-06: 0; 2024-09-06: 0
Estimate To Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimate at Completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Approved Budget | 0
Variance at Completion (Approved Budget-EAC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75% Notification
Total Approved Funding
Available Approved Funding (Approved less Actuals) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Variance Log
Month | Monthly Cost Variance | Comment
2023-10-01 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2023-11-01 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2023-12-02 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-01-02 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-02-02 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-03-04 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-04-04 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-05-05 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-06-05 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-07-06 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-08-06 | 0
Engineering Communications Survey - C | 0
Pre-Construction Activities - E | 0
Construction/Integration - F | 0
Acceptance Testing - G | 0
Operational Testing and Evaluation - I | 0
Project Management - Z | 0
2024-09-06
Month | Variance at Completion | Comment
2023-10-01 | 0
2023-11-01 | 0
2023-12-02 | 0
2024-01-02 | 0
2024-02-02 | 0
2024-03-04 | 0
2024-04-04 | 0
2024-05-05 | 0
2024-06-05 | 0
2024-07-06 | 0
2024-08-06 | 0
2024-09-06 | 0

## CPR Data
Task Order Title:
Task Order Number:
Period of Performance:
ACWP
WBS |  | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Engineering Communications Survey - C
E | Pre-Construction Activities - E
F | Construction/Integration - F
G | Acceptance Testing - G
I | Operational Testing and Evaluation - I
Z | Project Management - Z
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ETC
WBS |  | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Engineering Communications Survey - C
E | Pre-Construction Activities - E
F | Construction/Integration - F
G | Acceptance Testing - G
I | Operational Testing and Evaluation - I
Z | Project Management - Z
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BCWS
WBS |  | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Engineering Communications Survey - C
E | Pre-Construction Activities - E
F | Construction/Integration - F
G | Acceptance Testing - G
I | Operational Testing and Evaluation - I
Z | Project Management - Z
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BCWP
WBS |  | 2023-10-01 | 2023-11-01 | 2023-12-02 | 2024-01-02 | 2024-02-02 | 2024-03-04 | 2024-04-04 | 2024-05-05 | 2024-06-05 | 2024-07-06 | 2024-08-06 | 2024-09-06 | 2024-10-07 | 2024-11-07 | 2024-12-08 | 2025-01-08 | 2025-02-08 | 2025-03-11 | 2025-04-11 | 2025-05-12 | 2025-06-12 | 2025-07-13 | 2025-08-13 | 2025-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Engineering Communications Survey - C
E | Pre-Construction Activities - E
F | Construction/Integration - F
G | Acceptance Testing - G
I | Operational Testing and Evaluation - I
Z | Project Management - Z
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0