## ER and D&D Scoring Matrix
CDAT - Environmental Restoration Projects - CERCLA/RCRA
(Including D&D Projects Accomplished under CERCLA)
|  |  |  | CERCLA Preliminary Analysis/Site Investigation or RCRA Facility Assessment (CD‑0 /1) |  | CERCLA Remedial Investigation/ Feasibility Study (or EE/CA) or RCRA Facility Investigation/ Corrective Measures Study (CD-1/2) |  | CERCLA Remedial Design/Remedial Action or RCRA Corrective Measure (CD-2/3)
|  | Weighting Designation | Weighting Factor | Expected Maturity Value | Target Score | Expected Maturity Value | Target Score | Expected Maturity Value | Target Score
A. COST
A1 | Cost Estimate | H | 7.5 | 1 | 7.5 | 2 | 15 | 5 | 37.5
A2 | Cost Risk/Contingency Analysis | P | 3 | 1 | 3 | 2 | 6 | 5 | 15
A3 | Funding Requirements/Profile | H | 7.5 | 1 | 7.5 | 2 | 15 | 5 | 37.5
A4 | Independent Cost/Schedule Review | P | 3 | N/A | 0 | 2 | 6 | 5 | 15
A5 | Life Cycle Cost | P | 3 | 1 | 3 | 2 | 6 | 5 | 15
A6 | Forecast Cost at Completion | P | 3 | N/A | 0 | 3 | 9 | 5 | 15
A7 | Cost Estimate for Next Phase Work Scope | P | 3 | 5 | 15 | 5 | 15 | 5 | 15
Subtotal Cost Element |  |  |  |  | 36 |  | 72 |  | 150
B. SCHEDULE
B1 | Project Schedule | H | 7.5 | 1 | 7.5 | 2 | 15 | 5 | 37.5
B2 | Major Milestones | P | 3 | 1 | 3 | 2 | 6 | 5 | 15
B3 | Resource Loading | P | 3 | 1 | 3 | 1 | 3 | 5 | 15
B4 | Critical Path Management | H | 7.5 | 1 | 7.5 | 1 | 7.5 | 5 | 37.5
B5 | Schedule Risk/Contingency Analysis | P | 3 | 1 | 3 | 1 | 3 | 5 | 15
B6 | Forecast of Schedule at Completion | P | 3 | 1 | 3 | 3 | 9 | 5 | 15
Scope
B7 | Schedule for Next Phase Work | P | 3 | 5 | 15 | 5 | 15 | 5 | 15
Subtotal Schedule Element |  |  |  |  | 42 |  | 58.5 |  | 150
C. SCOPE/TECHNICAL
C1 | Preliminary Assessments/Site Investigation | P | 2.2 | 5 | 10.9 | 5 | 10.9 | 5 | 10.9
C2 | Remedial Investigation/RCRA Facility Investigation (includes Baseline Risk Assessment) | P | 2.2 | 2 | 4.4 | 5 | 10.9 | 5 | 10.9
C3 | Feasibility Study (FS)/Corrective Measures Study (CMS) | H | 3.5 | 2 | 7 | 5 | 17.5 | 5 | 17.5
C4 | Engineering Evaluation/Cost Analysis of Removal Actions/Early Action | H | 3.5 | 2 | 7 | 5 | 17.5 | 5 | 17.5
C5 | Performance Assessment (PA) | P | 2.2 | 1 | 2.2 | 5 | 10.9 | 5 | 10.9
C6 | Technology Needs Identified and Available | P | 2.2 | 3 | 6.6 | 4 | 8.8 | 5 | 10.9
C7 | Technology Needs Demonstrated | H | 3.5 | N/A | 0 | 1 | 3.5 | 5 | 17.5
C8 | Performance Requirements | P | 2.2 | 1 | 2.2 | 3 | 6.6 | 5 | 10.9
C9 | Waste Acceptance Criteria (WAC) | P | 2.2 | 1 | 2.2 | 3 | 6.6 | 5 | 10.9
C10 | Proposed Plan (PP) | P | 2.2 | 1 | 2.2 | 2 | 4.4 | 5 | 10.9
C11 | CERCLA Record of Decision (ROD)/Action Memo (AM) | P | 2.2 | N/A | 0 | 2 | 4.4 | 5 | 10.9
C12 | Natural Phenomena | P | 2.2 | 1 | 2.2 | 3 | 6.6 | 5 | 10.9
C13 | Remedial Design/D&D Plans | H | 3.5 | N/A | 0 | N/A | 0 | 5 | 17.5
C14 | Equipment Needs | P | 2.2 | N/A | 0 | 2 | 4.4 | 5 | 10.9
C15 | Remedial/D&D Design/Plans, Technical, and Safety-related Reviews for this phase | P | 2.2 | N/A | 0 | 4 | 8.8 | 5 | 10.9
C16 | Waste Storage, Packaging and Transportation | H | 3.5 | 1 | 3.5 | 2 | 7 | 5 | 17.5
C17 | Training Requirements | P | 2.2 | N/A | 0 | 1 | 2.2 | 5 | 10.9
C18 | Waste Characterization and Disposition | H | 3.5 | 1 | 3.5 | 3 | 10.5 | 5 | 17.5
C19 | Pollution Prevention & Waste Minimization | H | 3.5 | N/A | 0 | 2 | 7 | 5 | 17.5
C20 | Environmental Monitoring Plan | P | 2.2 | 1 | 2.2 | 2 | 4.4 | 5 | 10.9
C21 | NEPA Documentation (RCRA Projects) | H | 3.5 | 1 | 3.5 | 3 | 10.5 | 5 | 17.5
C22 | End Point Criteria and Closure Plan/Permit Modification | H | 3.5 | 1 | 3.5 | 3 | 10.5 | 5 | 17.5
C23 | Long Term Surveillance and Monitoring Plan/Post Disposition Monitoring Plan | P | 2.2 | N/A | 0 | 2 | 4.4 | 5 | 10.9
C24 | Permits, Licenses, and Regulatory Approvals | H | 3.5 | N/A | 0 | 3 | 10.5 | 5 | 17.5
C25 | Plot Plan | P | 2.2 | 2 | 4.4 | 4 | 8.8 | 5 | 10.9
C26 | Site/Facility Characterization (Including Surveys and Soil Tests) and radioactive inventory | P | 2.2 | 2 | 4.4 | 3 | 6.6 | 5 | 10.9
Subtotal Scope/Technical Element |  |  |  |  | 71.9 |  | 204.2 |  | 349.4
D. MANAGEMENT PLANNING AND CONTROL
D1 | Mission Need Statement | H | 2.9 | 5 | 14.3 | 5 | 14.3 | 5 | 14.3
D2 | Acquisition Strategy/ Plan | H | 2.9 | 1 | 2.9 | 5 | 14.3 | 5 | 14.3
D3 | Key Project Assumptions | P | 1.5 | 1 | 1.5 | 4 | 6.2 | 5 | 7.7
D4 | Project Execution Plan (PEP) | H | 2.9 | 1 | 2.9 | 3 | 8.6 | 5 | 14.3
D5 | Integrated Project Team (IPT) and Charter | P | 1.5 | 1 | 1.5 | 3 | 4.6 | 5 | 7.7
D6 | Integrated Regulatory Oversight Program | P | 1.5 | 1 | 1.5 | 4 | 6.2 | 5 | 7.7
D7 | Baseline Change Control | H | 2.9 | 1 | 2.9 | 4 | 11.4 | 5 | 14.3
D8 | Project Control | P | 1.5 | N/A | 0 | 3 | 4.6 | 5 | 7.7
D9 | Project Work Breakdown Structure (WBS) | P | 1.5 | 1 | 1.5 | 4 | 6.2 | 5 | 7.7
D10 | Resources Required (People/Material) for Next Phase | P | 1.5 | 4 | 6.2 | 5 | 7.7 | 5 | 7.7
D11 | Configuration Management | H | 2.9 | 2 | 5.7 | 3 | 8.6 | 5 | 14.3
D12 | Project Risk Management Plan/Assessment | H | 2.9 | 1 | 2.9 | 3 | 8.6 | 5 | 14.3
D13 | Quality Assurance Program | P | 1.5 | 2 | 3.1 | 4 | 6.2 | 5 | 7.7
D14 | Value Engineering, Trade-Off, and Optimization Studies | P | 1.5 | 1 | 1.5 | 3 | 4.6 | 5 | 7.7
D15 | Procurement Packages | P | 1.5 | N/A | 0 | 1 | 1.5 | 5 | 7.7
D16 | Project Acquisition Process | P | 1.5 | 1 | 1.5 | 5 | 7.7 | 5 | 7.7
D17 | Funds Management | P | 1.5 | 1 | 1.5 | 3 | 4.6 | 5 | 7.7
D18 | Reviews/Assessments | P | 1.5 | 2 | 3.1 | 5 | 7.7 | 5 | 7.7
D19 | Stakeholder Program | H | 2.9 | 2 | 5.7 | 4 | 11.4 | 5 | 14.3
D20 | Inter-Site and On-Site Coordination | P | 1.5 | 2 | 3.1 | 3 | 4.6 | 5 | 7.7
Subtotal Management Planning and Control Element |  |  |  |  | 63.3 |  | 149.6 |  | 200.2
E. SAFETY
E1 | Hazard Analysis/Safety Documentation | P | 5 | 1 | 5 | 3 | 15 | 5 | 25
E2 | Integrated Safeguards and Security Planning | P | 5 | 1 | 5 | 3 | 15 | 5 | 25
E3 | ES&H Management Planning (Including ISM) | H | 15 | N/A | 0 | 2 | 30 | 5 | 75
E4 | Emergency Preparedness | P | 5 | N/A | 0 | 1 | 5 | 5 | 25
Subtotal Safety Element |  |  |  |  | 10 |  | 65 |  | 150
TOTAL |  |  |  |  | 223.2 |  | 549.3 |  | 999.6