## Completed Projects
Completed Projects
Site | Project Type | PARSID | Project Name | Approved Budget ($) | Actual Cost ($) | Completion Date Approved | Completion Date Actual | Cost Success | Schedule Success | Complete Scope
Carlsbad | Facility Construction | 1024 | Safety Significant Confinement Ventilation System (WIPP) | 288000000 | 485000000 | 2022-11-30 | 2025-03-12 | No | No | Yes
ETTP | Decontamination and Decommissioning | 1044 | K-27 Demolition Project | 98201000 | 59500000 | 2018-12-31 | 2017-09-25 | Yes | Yes | Yes
|  | 1097 | Nuclear Facility D&D - ETTP (Program) | 275685000 | 200436000 |  | 2019-09-25 | Yes | No | Yes
|  | 897 | K-25 D & D | 479400000 | 1107000000 | 2017-09-30 | 2015-01-09 | No | Yes | Yes
|  | 1125 | Poplar Creek Area Facility Demolition Project | 95570000 | 89000000 | 2019-09-30 | 2019-09-25 | Yes | Yes | Yes
|  | 1136 | Technetium-99 Contamination Remedial Action Project | 94200000 | 53000000 | 2022-05-30 | 2020-07-28 | Yes | Yes | Yes
KAPL | Decontamination and Decommissioning | 688 | Nuclear Facility D&D - Separations Process Research Unit | 78600000 | 225400000 | 2012-09-30 | 2020-06-18 | No | No | No
Oak Ridge | Decontamination & Decommissioning | 653 | K-25 Decontamination and Decommissioning Project | 479400000 | 1107000000 | 2017-09-30 | 2015-01-09 | No | Yes | Yes
ORP | Facility Construction | 1178 | Tank-Side Cesium Removal System Demonstration Subproject | 164000000 | 135000000 | 2022-07-25 | 2022-04-12 | Yes | Yes | Yes
Portsmouth | Demolition | 1163 | X-326 Process Building Demolition Project | 160000000 | 131500000 | 2025-10-31 | 2024-07-03 | Yes | Yes | Yes
| Facility Construction | 1047 | On-Site Waste Disposal Facility - Initial Infrastructure & Cells 1, 4 & 5 Liner Construction | 285000000 | 247800000 | 2024-05-31 | 2022-08-16 | Yes | Yes | Yes
Richland | Decontamination and Decommissioning | 402 | Plutonium Finishing Plant (PFP) Decontamination and Dismantlement - ARRA Base | 330200000 | 343000000 | 2011-09-30 | 2020-04-10 | Yes | No | Yes
|  | 673 | Nuclear Facility D&D - River Corridor Closure Project | 2251500000 | 1850000000 | 2019-09-30 | 2018-11-27 | Yes | Yes | Yes
| Demolition | 1043 | Plutonium Finishing Plant Demolition Project | 72600000 | 204000000 | 2018-08-31 | 2022-01-19 | No | No | Yes
| Restoration or Remediation | 1011 | KW Basin Sludge Removal Project | 311000000 | 291000000 | 2019-11-30 | 2018-06-04 | Yes | Yes | Yes
SRS | Facility Construction | 389 | Salt Waste Processing Facility | 900000000 | 2260000000 | 2013-11-30 | 2020-08-17 | No | No | Yes
|  | 538 | Saltstone Disposal Unit #6 | 143166420 | 121700000 | 2018-11-30 | 2017-07-18 | Yes | Yes | Yes
|  | 1068 | Saltstone Disposal Unit #7 | 159000000 | 127000000 | 2022-03-31 | 2021-07-21 | Yes | Yes | Yes
|  | 1120 | Saltstone Disposal Units 8 and 9 | 280000000 | 217700000 | 2024-09-30 | 2024-03-19 | Yes | Yes | Yes
| Restoration or Remediation | 1033 | D-Area Ash Project | 74200000 | 68800000 | 2020-07-31 | 2019-06-10 | Yes | Yes | Yes