## EVMS Cert Status
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Carlsbad Field Office | Waste Isolation Pilot Project Management and Operating Contract | Salado Isolation Mining Contractors (SIMCO) 89303322DEM000077 (LLC Team: Bechtel) | 11/08/2022 to 11/07/2026 | Firm Fixed Price/Time and Materials/ Task Orders | Not Certified: The previous WIPP M&O Contract, DE‐EM0001971, held by Nuclear Waste Partnership, LLC , whose previous EVMS certification was utilized by to the new M&O contractor, Salado Isolation Mining Contractors (SIMCO), LLC.) beginning on Feb 4th, 2023. However, SIMCO was not able to meet the DOE Order 413.3B requirement for an EIA‐748 compliant EVMS. As a result, the Department Office of Project Management (PM) issued a memorandum March 1, 2024, changing the SIMCO EVMS status from “Under Review” to “Not Certified”. The Project Management Risk Committee endorsed CBFO's request for a temporary exemption for the requirement to manage mature (post CD-3) projects with the condition that alternative Project Controls methods be put in place on May 8, 2024 EM-1 approved the exemption through a memorandum issued on Jun 6, 2024.
| Carlsbad Transportation Services (WIPP) | CAST Specialty Transportation, Inc. 89303322DEM000076 | 06/16/2022 to 6/15/2027 | Indefinite Delivery/ Indefinite Quantity | Earned Value Management System NOT Required
| Carlsbad Technical Assistance Contract (CTAC) | Navarro Research and Engineering, Inc 89303321DEM000063 | 07/01/2021 to 06/30/2031 | Indefinite Delivery/ Indefinite Quantity | Earned Value Management System NOT Required
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Environmental Management Consolidated Business | Energy Technology Engineering Center Site -Site Environmental Monitoring, Decontamination and Demolition, and Surveillance and Maintenance (ETEC) | North Wind, Portage Inc. DE-EM0000837 | 08/01/2014 to 06/30/2024 | Indefinite Delivery/ Indefinite Quantity | Earned Value Management System NOT Required
Environmental Management Consolidated Business | Moab Site- Environmental Remediation of the Moab Uranium Mill Tailings | North Wind Portage, Inc. 89303322DEM000073 | 02/03/2022 to 02/02/2032 | Indefinite Delivery/ Indefinite Quantity | Earned Value Management System NOT Required
| Nevada- Environmental Program Services | Navarro, Inc. 89303320DEM000037 | 10/01/2020 to 09/30/2030 | Indefinite Delivery/ Indefinite Quantity | Certification Not Required: Not certified because the contract does not have a capital asset project that requires a certified EVMS.
Environmental Management Consolidated Business | West Valley Demonstration Project Interim End State | CH2MHill-Babcock and Wilcox West Valley, LLC DE-EM0001529 | 08/29/2011 to 02/28/2025 | Cost-Plus Award Fee (CPAF) w/PBI | Certification Waived: CH2M Hill-B&W West Valley: EVMS certification is required for the contract. The site has only one capital project of sufficient size to warrant EVMS certification by the Department’s certification authority, the DOE Office of Project Management (PM). On June 16, 2020, the Under Secretary for Science (S- 4) approved the DOE Order 413.3B exemption request to allow the WVDP MPPB Demolition project to proceed to CD-2/3 without employing a certified EVMS system and instead manage the project via alternate project controls and a contractor maintained EVMS.
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Environmental Management Consolidated Business | Los Alamos Legacy Cleanup Contract | LLC Team: Stoller Newport News Nuclear Los Alamos, LLC and BWXT Technical Services Group, Inc. 89303318CEM000007 | 04/30/2018 to 04/29/2026 | Indefinite Delivery/ Indefinite Quantity | Certification Not Required: N3B is Not yet certified because the contract does not have a capital asset project that requires a certified EVMS.
Hanford Procurement Office (Office of River Protection and Richland Operations Office) | Waste Treatment Plant (WTP) Construction of the Hanford Tank Waste Treatment and Immobilization Plant | Bechtel National Inc. DE-AC27-01RV14136 | 12/11/2000 to 09/30/2024 | Cost Plus Award Fee | Under Review by PM: As of April 26, 2024, PM, in coordination with ORP, completed its review of the BNI corrective action management plan (CAMP) to include root cause analyses, corrective actions, exit criteria, and deliverables developed in response to corrective action requests (CAR) and discrepancy reports (DR).” PM was unable to validate the final effectiveness of all corrective actions so while the surveillance is closed, PM will assess compliance with EIA-748 of the BNI EVMS when it conducts a new certification review of BNI’s EVMS for use on the direct feed high-level waste (DFHLW) phase of the project.
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Hanford Procurement Office (Office of River Protection and Richland Operations Office) | Hanford Integrated Tank Disposition Contract | H2C- Hanford Tank Waste Operations & Closure, LLC ( 89303324DEM000096) (LLC Team: BWXT Technical Services Group, Inc., Amentum Environment & Energy, Inc., Fluor Federal Services, Inc.) | 02/24/2024 to 02/28/2034 | Indefinite Delivery/ Indefinite Quantity | Certified: At the end of February 2025, the WRPS contractor at HFO transitioned to H2C, also know as HANFORD TANK WASTE OPERATIONS & CLOSURE, LLC. H2C plans to "blue-sheet" the current certified EVMS system.
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Hanford Procurement Office (Office of River Protection and Richland Operations Office) | Hanford 222-S Laboratory Contract | Hanford Laboratory Management and Integration, LLC 89303320CEM000075 (LLC Members Navarro Research and Engineering, Inc., and Advanced Technologies and Laboratories International) | 09/20/2020 to 09/19/2025 | Cost Plus Award Fee | Certification Not Required: Not yet certified because the contract does not have a capital asset project that requires a certified EVMS.
| HPMC Corporation (OCC Med Occupational Medical Services for Hanford Site) | HPM Corporation 89303919DEM000005 | 12/31/2018 to 12/31/2023 | Firm Fixed Price, Cost Reimbursement, and IDIQ | Earned Value Management System NOT Required
| HPMC Corporation (OCC Med Occupational Medical Services for Hanford Site) | Inomedic Health Applications (IHA) 89303324DEM000093 | 11/2/2023 to 11/1/2026 | FFP, CR, and IDIQ | Earned Value Management System NOT Required
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Hanford Procurement Office (Office of River Protection and Richland Operations Office) | Hanford Mission Essential Services Contract (Infrastructure and Site services) | Hanford Mission Integration Solutions 89303320DEM000031 | 08/17/2020 to 08/16/2025 | Cost-Plus Award Fee (CPAF) w/PBI | Certification Not Required: Not yet certified because the contract does not have a capital asset project that requires a certified EVMS.
| Central Plateau Cleanup Contract (CPCC) (Management of site operations for Richland cleanup facilities) | Central Plateau Cleanup Company 89303320DEM000030 (LLC Team: AECOM, Fluor and Atkins) | 12/12/2019 to 12/11/2029 | Indefinite Delivery/ Indefinite Quantity | Certified: CPCC adopted a certified EVM System from the previous contractor, CH2M HILL Plateau Remediation Company (CHPRC). Currently, the CPCC contract does not have a capital asset project that requires a certified EVMS.
Idaho Operations Office | Idaho Cleanup Project End State Contract (ICP) | Idaho Environmental Coalition, LLC 89303321DEM000061 (LLC Team: Jacobs, North Wind Portage) | 10/1/2021 to 09/30/2031 | Indefinite Delivery/ Indefinite Quantity | Under Review by PM: PM-30 will use the maturity model and environmental assessment using the Integrated Project/Program Management (IP2M) Maturity and Environment Total Risk Rating (METRR) tool to assess their EVMS. The draft charter defines all the expected milestones for delivery, meetings, data deliveries, and other details needed to complete the their EVMS Compliance certification.
| Physical Security Services | Protection Strategies, Inc. (PSI) (SDVOSB) GS-07F0442N/89243221FEM400010 (TO) | 10/01/2021 to 09/30/2024 | Time and Materials | Earned Value Management System NOT Required
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Oak Ridge Office | U-233 Disposition Project | Isotek Systems, LLC DE-AC05-04OR22860 (LLC Team: Atkins) | 10/09/2003 to 12/31/2024 | Fixed Price | Certified
| OF200 Mercury Treatment System | APTIM/NW Construction Joint Venture 89303319CEM000041 | 12/6/2018 to 12/25/2023 | Firm Fixed Price | Earned Value Management System NOT Required
| Oak Ridge Reservation Cleanup Contract (ORRCC) | United Cleanup Oak Ridge, LLC (UCOR) 89303322DEM000067 | 10/27/2021 to 10/26/2031 | Indefinite Delivery/ Indefinite Quantity (Task Orders) | EVMS Under Review: UCOR is using the EVMS from the prior contractor, URS CH2M Oak Ridge, LLC (former UCOR). This EVMS will require an implementation review because the total contract value for the OF200 Mercury Treatment Facility project exceeds $100M (currently $224M with BCP proposed at $324M). According to DOE -PM, The OF200 MTF project may participate in an EVMS review prior to achieving CD-4.EVMS aasessment scheduled for the second quarter of FY2025.
Oak Ridge Office | Tech Support Service | Professional Project Services, Inc. GS-00F-112CA / 89303323FEM400324(TO) | 02/23/2023 – 02/22/2024 | Time & Materials, Task Orders | Earned Value Management System NOT Required
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Portsmouth Paducah Project Office | (DUF6) Conversion Facilities Operation of Depleted Uranium Hexafluoride | Mid-America Conversion Services, LLC DE-EM0004559 (LLC Team: Atkins, Westinghouse, Fluor) | 11/03/2016 to 01/31/2024 | Cost Plus Award Fee and Fixed Price CLINs | Certified: Contract calls for either an Earned Value Management System or an alternate performance management method. MCS established an EVMS, which is not certified because the contract does not have a capital asset project that requires a certified EVMS.
| Portsmouth Infrastructure Services | North Wind Dynamics, LLC 89303321DEM000065 | 01/03/2022 to 12/18/2024 | FFP w IDIQ, LH, and CR CLINs | Earned Value Management System NOT Required
| Paducah GDP Deactivation & Remediation | Four Rivers Nuclear Partnership, LLC DE-EM0004895 (LLC Team: Jacobs, Fluor, BWX Technologies) | 06/20/2017 to 06/19/2025 | Cost Plus Award Fee | Certification Not Required(Self Certified): Not yet certified because the contract does not have a capital asset project that requires a certified EVMS. Four Rivers Nuclear Partnership, LLC recently completed a self-surveillance/compliance review and found their EVMS adequate.
Portsmouth Paducah Project Office | Paducah Infrastructure Services | Swift and Staley, Inc. DE-EM0003733 | 10/01/2015 to 07/31/2024 | FFP w IDIQ, LH, and CR CLINs | Earned Value Management System NOT Required
| Portsmouth GDP Decontamination and Decommissioning (D&D) | Fluor-Babcock and Wilcox Portsmouth, LLC DE-AC30-10CC40017 (LLC Team: Fluor, BWXT) | 08/16/2010 to 01/31/2024 | Cost Plus Award Fee | Certified: Fluor B&W Portsmouth LLC (FBP): Fluor B&W (Portsmouth D&D) successfully demonstrated compliance of its EVMS & the Office of Project Management certified them on Jan 30, 2020.
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Portsmouth Paducah Project Office | Portsmouth Paducah Project Office Technical Support Services | E-TAS/ 89303319CEM000055 | 03/31/2023 to 03/31/2025 | Time and Materials, IDIQ CLIN for Firm Fixed Price Task Orders | Earned Value Management System NOT Required
Savannah River Site Office | Savannah River Site Management and Operation (M&O) | Savannah River Nuclear Solutions, LLC DEO-AC09-08SR22470 (LLC Team: Fluor, Newport News Nuclear, Honeywell International) | 01/10/2008 to 09/30/2026 | Cost-Plus Award Fee (M&O) | Not Certified: Savannah River Nuclear Solutions, LLC requires Earned Value Management System and Certification and is not currently certified.
| Paramilitary Services | Savannah River Security Contract (Paramilitary SVC/Centerra Group, LLC) 89303323DEM000088 | 07/15/2023 to 5/14/2033 | Cost Plus Award Fee | Earned Value Management System NOT Required
Site | Contract Description | Contractor and Contract Number | Current Contract Period | Contract Type | Certification Status
Savannah River Site Office | Savannah River National Lab (SRNL) M&O | Battelle Savannah River Alliance (BSRA) 89303321CEM000080 | 02/16/2021 to 02/15/2026 | Cost Plus Award Fee | Earned Value Management System NOT Required
Savannah River Site Office | Savannah River Site Integrated Mission Completion Contract | Savannah River Mission Completion, LLC 89303322DEM000068 | 10/27/2021 to 10/26/2031 | Indefinite Delivery/ Indefinite Quantity | Certified: Savannah River Mission Completion, LLC is currently using an EVMS that has been previously certified. Under Review by PM: PM-30 will be using the Integrated Project/Program Management (IP2M) Maturity and Environment Total Risk Rating (METRR) tool as part of the currently ongoing review to determine their EVMS Compliance certification.