## Acronyms
Acronym | Full text
AT | Acquisition Team
CO | Contracting Officer
CPARS | Contractor Performance Assessment Reporting System
CUI | Controlled Unclassified Information
DOE | Department of Energy
ECM | Energy Conservation Measure
ESCO | Energy Service Company
FPE | Federal Project Executive
FY | Fiscal Year
GFO | Golden Field Office
HQ | Headquarters
IDIQ | Indefinite Delivery Indefinite Quantity
IGA | Investment Grade Audit
M&V | Measurement and Verification
NOITA | Notice of Intent to Award
NOO | Notice of Opportunity
OMRR | Operations, Maintenance, Repair, and Replacement
PA | Preliminary Assessment
PF | Project Facilitator
RRPM | Risk, Responsibility, and Performance Matrix
TO | Task Order

## ESPC Schedule (standard)
Project Name: | Jones Laboratories
Date of Last Update: | 2024-02-15
[5 empty] | Estimated | Actual
Stand alone tasks - not critical path |  |  | Time from Phase 1 to TO Award: |  | 20 | 0
Tasks that must be done before the following task - Critical Path
Key Milestones that require stakeholder approval and Contracting Officer action
Activity | Timeline |  | Completion Dates |  |  |  | ESCO | Gov't Site/Agency | FEMP Support | PF | GFO
| Calendar Days, Working Days1 |  | Estimated Start | Actual | Estimated End | Actual End
Start Date |  |  | 02/15/2024 |  | 2025-09-22
Phase 1 - Project Planning | 30-60 | Total Elapsed Days
Contact FPE to assist with training, project planning, and latest FEMP Guidance Documents | 3 | 5 | 02/15/2024 |  | 2024-02-20 |  |  | Outreach | X
Review FEMP Best Practices Document and FAQs | 2 | 11 | 2024-02-22 |  | 2024-02-26 |  |  | X | X
Review the DOE guidance "Federal ESPC Process Phase 1: Acquisition Planning" | 1 | 11 | 2024-02-23 |  | 2024-02-26 |  |  | X | X
Establish Acquisition Team (AT) and develop acquisition plan | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X | Support
Gather preliminary data for NOO - Utility spend (1 year), utility usage, building square footage, age, type. | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X
Create Milestone Plan | 3 | 15 | 2024-02-27 |  | 2024-03-01 |  |  | X | Support
AT develops NOO & source selection plan | 10 | 35 | 2024-03-07 |  | 2024-03-21 |  |  | X | Support
Site works with FPE to request a Project Facilitator (PF) | 5 | 35 | 2024-03-14 |  | 2024-03-21 |  |  | X | X
Golden Field Office (GFO) begins PF procurement | 60 | 105 | 2024-03-07 |  | 2024-05-30 |  |  | X | Support
Provide written notification to DOE IDIQ CO of intent to issue NOO | 3 | 29 | 2024-03-12 |  | 2024-03-15 |  |  | X | Support
Contracting Officer (CO) issues NOO to sam.gov and/or other public procurement websites | 22 | 57 | 2024-03-13 |  | 2024-04-12 |  |  | X | Support
Coordinate ESPC Training for project team | 5 | 40 | 2024-03-19 |  | 2024-03-26 |  |  | X | X
Phase 2 - Selecting the ESCO - preliminary | 45
ESCOs submits Expression of Interest (EOI) responses to NOO | 25 | 62 | 2024-03-13 |  | 2024-04-17 |  | X
Acquisition team down selection to multiple ESCOs | 20 | 90 | 2024-04-17 |  | 2024-05-15 |  |  | X |  | X
ESCO down selection notification & notice to proceed with finalists | 1 | 91 | 2024-05-15 |  | 2024-05-16 |  |  | X
Phase 2 - Selecting final ESCO
ESCOs submit further info and/or respond to oral interviews | 10 | 105 | 2024-05-16 |  | 2024-05-30 |  | X
Acquisition Team reviews further information and down selects to one ESCO for PA | 10 | 119 | 2024-05-30 |  | 2024-06-13 |  |  | X |  | X
CO sends down selection notice to unsuccessful ESCO offerors | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X
CO issues Successful Offer Letter to selected ESCO for Preliminary Assessment (PA) | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X |  |  | Receives notice from site/agency CO
ESCO notifies CO of intent to proceed to PA | 1 | 123 | 2024-06-14 |  | 2024-06-17 |  | X
Phase 2 - ESCO Performs Preliminary Assessment | 60
Begin contractor site access and clearance process (if required) | 5 | 130 | 2024-06-17 |  | 2024-06-24 |  | X | X
Ensure Government escorts are available for site visits (if required) | 5 | 130 | 2024-06-17 |  | 2024-06-24 |  |  | X
Preliminary Assessment (PA) kickoff meeting with ESCO, PF, FPE | 1 | 132 | 2024-06-25 |  | 2024-06-26 |  | X | X | X | X
Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 5 | 139 | 2024-06-26 |  | 2024-07-03 |  | X
Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X
Weekly or Biweekly progress meetings | [6 empty] | X | X | X | X
Site receives PA | 45 | 202 | 2024-07-03 |  | 2024-09-04 |  | X
AT convenes and reviews PA results | 5 | 209 | 2024-09-04 |  | 2024-09-11 |  |  | X | Support | X
PA Comments (from gov't) | 20 | 237 | 2024-09-11 |  | 2024-10-09 |  |  | X | X | X
PA Comment Response (from ESCO) | 15 | 258 | 2024-10-09 |  | 2024-10-30 |  | X
CO issues NOITA & Draft TO RFP | 5 | 265 | 2024-10-30 |  | 2024-11-06 |  |  | X
Phase 3 - Investment Grade Audit | 175
IGA Kickoff Meeting | 1 | 301 | 2024-12-11 |  | 2024-12-12 |  | X | X | X | X
Issue draft TORFP | 1 | 278 | 2024-11-18 |  | 2024-11-19 |  | X | X
Begin contractor site access and clearance process (if required) | 0 | 265 | 2024-11-06 |  | 2024-11-06 |  |  | X
Ensure Government escorts are available for site visits (if required) | 0 | 265 | 2024-11-06 |  | 2024-11-06 |  |  | X
Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 10 | 315 | 2024-12-12 |  | 2024-12-26 |  | X
Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X | Support
Weekly or Biweekly progress meetings | [6 empty] | X | X | Support | X
ESCO Milestone project reviews, as needed. Concurrence on RRPM items in DOE IDIQ contract. | [6 empty] | X | Support
ECM Scope Workshop | 1 |  | 2025-03-06 |  | 2025-03-07 |  | X | X | S | X
M&V Workshop | 1 |  | 2025-04-17 |  | 2025-04-18 |  | X | X | S | X
OMRR Workshop | 1 |  | 2025-03-12 |  | 2025-03-13 |  | X | X | S | X
ESCO completes IGA and submits | 100 | 455 | 2024-12-26 |  | 2025-05-15 |  | X
Government review and comments | 25 | 490 | 2025-05-15 |  | 2025-06-19 |  |  | X |  | X
ESCO Comment response | 25 | 525 | 2025-06-19 |  | 2025-07-24 |  | X
ESCO revisions to comments, issues Final Proposal | 10 | 539 | 2025-07-24 |  | 2025-08-07 |  | X
Phase 3: Negotiation and Award | 30
AT / CO requests and obtains executive approval for Final Proposal | 10 | 553 | 2025-08-07 |  | 2025-08-21 |  |  | X
DOE IDIQ CO Review of Final Proposal | 10 | 504 | 2025-06-19 |  | 2025-07-03 |  |  | X |  |  | X
Congressional Notification (If required) (31 calendar days) | 23 | 572 | 2025-08-07 |  | 2025-09-09 |  |  | X
Project Negotiations | 10 | 567 | 2025-08-21 |  | 2025-09-04 |  | X | X
Finalize TO Award documents, Final Task Order schedules (includes all reviews and approvals) | 5 | 574 | 2025-09-04 |  | 2025-09-11 |  | X | X |  | X
Lock Interest Rate | 5 | 581 | 2025-09-11 |  | 2025-09-18 |  | X | Direct ESCO
ESCO provides revised Task Order Schedules with locked interest rate | 1 | 582 | 2025-09-18 |  | 2025-09-19 |  |  | X
Sign Task Order | 1 | 585 | 2025-09-19 |  | 2025-09-22 |  | X | X
1. Days in this column are not additive. Some occur simultaneously. Number of day are approximate and suggested dates for expedited DOE ESPC IDIQ.
Formulas:
Estimated End = WORKDAY([Completion Dates],[Timeline])
Completion Dates = WORKDAY([Estimated End, row above],[Timeline])
Completion Dates = WORKDAY([Completion Dates, row above],[Timeline])

## EPC Direct
| Project Name: | Jones Laboratories
| Date of Last Update: | 2024-02-15
[6 empty] | Estimated | Actual
| Stand alone tasks - not critical path |  |  | Time from Phase 1 to TO Award: |  | 15 | 0
Tasks that must be done before the following task - Critical Path
Key Milestones that require stakeholder approval and Contracting Officer action
| Activity | Timeline |  | Completion Dates |  |  |  | ESCO | Gov't Site/Agency | FEMP Support | PF | GFO
|  | Calendar Days, Working Days1 |  | Estimated Start | Actual | Estimated End | Actual End
| Start Date |  |  | 02/15/2024 |  | 2025-04-30
| Phase 1 - Project Planning | 30-60 | Total Elapsed Days
1 | Contact FPE to assist with training, project planning, and latest FEMP Guidance Documents | 3 | 5 | 02/15/2024 |  | 2024-02-20 |  |  | Outreach | X
2 | Review FEMP Best Practices Document and FAQs | 2 | 11 | 2024-02-22 |  | 2024-02-26 |  |  | X | X
3 | Review the DOE guidance "Federal ESPC Process Phase 1: Acquisition Planning" | 1 | 11 | 2024-02-23 |  | 2024-02-26 |  |  | X | X
4 | Establish Acquisition Team (AT) and develop acquisition plan | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X | S
5 | Gather preliminary data for NOO - Utility spend (1 year), utility usage, building square footage, age, type. | 5 | 14 | 2024-02-22 |  | 2024-02-29 |  |  | X
6 | Create Milestone Plan | 3 | 15 | 2024-02-27 |  | 2024-03-01 |  |  | X | S
7 | AT develops NOO & source selection plan | 10 | 35 | 2024-03-07 |  | 2024-03-21 |  |  | X | S
8 | Site works with FPE to request a Project Facilitator (PF) | 5 | 35 | 2024-03-14 |  | 2024-03-21 |  |  | X | X
9 | Golden Field Office (GFO) begins PF procurement | 60 | 105 | 2024-03-07 |  | 2024-05-30 |  |  | X | S
10 | Provide written notification to DOE IDIQ CO of intent to issue NOO | 3 | 29 | 2024-03-12 |  | 2024-03-15 |  |  | X | S
11 | Contracting Officer (CO) issues NOO to sam.gov and/or other public procurement websites | 22 | 57 | 2024-03-13 |  | 2024-04-12 |  |  | X | S
12 | Coordinate ESPC Training for project team | 5 | 40 | 2024-03-19 |  | 2024-03-26 |  |  | X | X
| Phase 2 - Selecting the ESCO - preliminary | 45
1 | ESCOs submits Expression of Interest (EOI) responses to NOO | 25 | 62 | 2024-03-13 |  | 2024-04-17 |  | X
2 | Acquisition team down selection to multiple ESCOs | 20 | 90 | 2024-04-17 |  | 2024-05-15 |  |  | X |  | X
3 | ESCO down selection notification & notice to proceed with finalists | 1 | 91 | 2024-05-15 |  | 2024-05-16 |  |  | X
Phase 2 - Selecting final ESCO
1 | ESCOs submit further info and/or respond to oral interviews | 10 | 105 | 2024-05-16 |  | 2024-05-30 |  | X
2 | Acquisition Team reviews further information and down selects to one ESCO for PA | 10 | 119 | 2024-05-30 |  | 2024-06-13 |  |  | X |  | X
3 | CO sends down selection notice to unsuccessful ESCO offerors | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X
4 | CO issues Notice of Intent to Award to ESCO finalist | 1 | 120 | 2024-06-13 |  | 2024-06-14 |  |  | X |  |  | Receives notice from site/agency CO
5 | ESCO notifies CO of intent to proceed to IGA | 1 | 123 | 2024-06-14 |  | 2024-06-17 |  | X
| Phase 2 - ESCO Performs Preliminary Assessment and delivers with Presentation Format or agency issues NOITA and moves directly to Phase 3 - Investment Grade Audit | 45
| Begin contractor site access and clearance process (if required) | 1
| Ensure Government escorts are available for site visits. | 1
| Preliminary Assessment (PA) kickoff meeting with ESCO, PF, FPE | 1
| Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 12
| Requests for Information - ESCO issues and site responds. | Ongoing
Weekly or Biweekly progress meetings
| EPC Direct - Preliminary Assessment (PA) Presentation and Discussion, Comment/Response | 20
| AT convenes and reviews PA results | 5
| CO issues NOITA & Draft TO RFP | 5
| Phase 3 - Investment Grade Audit | 175
1 | IGA Kickoff Meeting | 1 | 159 | 2024-07-22 |  | 2024-07-23 |  | X | X | X | X
2 | Issue draft TORFP | 1 | 134 | 2024-06-27 |  | 2024-06-28 |  |  | X
3 | Begin contractor site access and clearance process (if required) | 0 | 133 | 2024-06-27 |  | 2024-06-27 |  | X | X
4 | Ensure Government escorts are available for site visits (if required) | 0 | 123 | 2024-06-17 |  | 2024-06-17 |  |  | X
5 | Contractor(s) conduct site visits to identify any Energy Conservation Measures (ECMs) | 10 | 173 | 2024-07-23 |  | 2024-08-06 |  | X
6 | Requests for Information - ESCO issues and site responds. | Ongoing | [5 empty] | X | S
7 | Weekly or Biweekly progress meetings | [6 empty] | X | X | S | X
8 | ESCO Milestone project reviews, as needed. Concurrence on RRPM items in DOE IDIQ contract. | [6 empty] | X | S
9 | ECM Scope Workshop | 1 |  | 2024-11-05 |  | 2024-11-06 |  | X | X | S | X
10 | M&V Workshop | 1 |  | 2024-12-03 |  | 2024-12-04 |  | X | X | S | X
11 | OMRR Workshop | 1 |  | 2024-12-03 |  | 2024-12-04 |  | X | X | S | X
12 | ESCO completes IGA and submits | 120 | 341 | 2024-08-06 |  | 2025-01-21 |  | X
13 | Government review and comments | 15 | 362 | 2025-01-21 |  | 2025-02-11 |  |  | X |  | X
14 | ESCO Comment response | 15 | 383 | 2025-02-11 |  | 2025-03-04 |  | X
15 | ESCO revisions to comments, issues Final Proposal | 10 | 397 | 2025-03-04 |  | 2025-03-18 |  | X
| Phase 3: Negotiation and Award | 30
1 | AT / CO requests and obtains executive approval for final proposal | 10 | 411 | 2025-03-18 |  | 2025-04-01 |  |  | X
2 | DOE IDIQ CO Review of Final Proposal | 10 | 376 | 2025-02-11 |  | 2025-02-25 | [5 empty] | X
3 | Congressional Notification (If required) (31 calendar days) | 24 | 431 | 2025-03-18 |  | 2025-04-21 |  |  | X
4 | Project Negotiations | 10 | 425 | 2025-04-01 |  | 2025-04-15 |  | X | X
5 | Finalize TO Award documents, Final Task Order schedules (includes all reviews and approvals) | 5 | 432 | 2025-04-15 |  | 2025-04-22 |  | X | X |  | X
6 | Lock Interest Rate | 5 | 439 | 2025-04-22 |  | 2025-04-29 |  | X | Direct ESCO
7 | ESCO provides revised Task Order Schedules with locked interest rate | 1 | 533 | 2025-07-31 |  | 2025-08-01 |  |  | X
8 | Sign Task Order | 1 | 440 | 2025-04-29 |  | 2025-04-30 |  | X | X
1. Days in this column are not additive. Some occur simultaneously. Number of day are approximate and suggested dates for expedited DOE ESPC IDIQ.
Formulas:
Estimated End = WORKDAY([Completion Dates],[Timeline])
Completion Dates = WORKDAY([Estimated End, row above],[Timeline])
Completion Dates = WORKDAY([Completion Dates, row above],[Timeline])