## Slide 1
Dept. of Energy
Project Management Office (PM)
SNIPPET 3-1: BUDGET VS FUNDS AND THE PMB
Notes: This EVMS Training Snippet, sponsored by the U.S. Department of Energy’s Project Management Office discusses the differences between Budgets and Funds and provides some confusing statements heard in contractor offices. The purpose is to provide a common understanding within DOE and among DOE contractors, and to provide consistency.

## Slide 2
Funds are Real Dollars being spent
and forecasted to be spent
Budgets are only used for measurement purposes.
It is the planning of the total resources required to satisfy the contractual requirements.
1
2
3
FUNDS = MONEY
BUDGET
IS A
METRIC
BUDGET
CAN’T BE
SPENT
CONCEPT OF BUDGET vs FUNDS
Notes: First we need to understand the concept of budget and funds. Budget cannot be spent. It is the planning of the total resources required to satisfy the contractual requirements. We only use budgets for measurement purposes, and treat them as a key project metric. Think of it as a yard stick.
Funding consists of real dollars that are used to ‘pay the bill’ so to speak. Funds are obligated on a contract and spent to cover the actual costs incurred to complete a project.
We will discuss the abbreviations, and how they compare to each other, later in this snippet.

## Slide 3
BUDGETS
FUNDS
BAC
TAB
CBB & PBB1
BCWS
BCWP
AUW
MR
UB
EAC
ETC
ACWP
NTE
Contingency
EVMS
BUDGET AND
FUNDS
TERMS
1 Refer to Snippet 1-11 Varying Project and Contract Structures or the DOE EVMS Gold Card for information relative to the relation of the Contract Budget Base (CBB) and Project Budget Base (PBB).
Notes: EVMS is comprised of many acronyms which will be explained more in later slides. In this slide you see the list of acronyms that contain budget, and those that are funding. As we said, budget terms are for measuring. Think of it like a yard stick. Budget is not the same as Funds, and unless a project was executed perfectly as planned, which is unlikely, the budget will not equal the funds.
While most of these terms are familiar, one new term is the acronym PBB. Refer to Snippet 1-11 Varying Project and Contract Structures or the DOE EVMS Gold Card for information relative to the relation of the Contract Budget Base (CBB) and Project Budget Base (PBB).

## Slide 4: PERFORMANCE BASELINE COMPONENTS
Performance Baseline (PB)
[Total Project Cost (TPC)]
Contingency
Contract Price
(CP)
DOE Other Direct
Project Costs
Color Key
FUNDS
BUDGET
Profit / Fee
Notes: The Performance Baseline Components chart is provided in the context of Budget versus Funds. Those elements in blue represent funds. Starting at the top, the Performance Baseline represents the Total Project Cost for DOE. This is broken down to three elements: DOE-held Contingency, the Contract Price issued to the contractor, and DOE-held reserves for Other Direct Project Costs. All of these elements, along with the Contractor’s profit or fee are all associated with funds.

## Slide 5: PERFORMANCE BASELINE COMPONENTS
Color Key
FUNDS
BUDGET
Performance Baseline (PB)
[Total Project Cost (TPC)]
Contingency
Contract Price
(CP)
DOE Other Direct
Project Costs
Total Allocated Budget (TAB) =
Contract Budget Base (CBB) or Project Budget Base (PBB) + Over Target Baseline (OTB)
Profit / Fee
Management Reserve (MR)
Performance Measurement Baseline (PMB)
Summary Level Planning Packages (SLPPs)
Control Accounts
(Distributed Budget)
Undistributed Budget (UB)
Work Packages (WPs)
Planning Packages (PPs)
Notes: The budget related components are in grey beginning with the Total Allocated Budget or TAB, which is based on the negotiated target cost for the effort under contract. The TAB equals the Contract Budget Base or Project Budget Base unless an Over Target Baseline has been approved. The CBB/PBB is the level at which budget is managed by the contractor. The contractor first places the entire CBB/PBB in Undistributed Budget (UB), which is part of the performance measurement baseline (PMB). The UB budget is then allocated to the control accounts, based on the estimates to perform the scope, Summary Level Planning packages, and management reserve. Notice that the Profit or Fee is both blue and grey. Fee is something that is budgeted for prior to being earned, but once earned it is paid using funds.

## Slide 6: CONTRACT FUNDING
$
Contract Funding is aligned to Actual Spending, or ACWP, and projected spending [Estimate at Completion (EAC)]
Cumulative Performance and remaining Baseline (BCWS) factor into the EAC
BCWP
ACWP
BCWS
Funding
Profile
Time Now
Notes: Contract Funding is a process used to secure payment to contractors for the actual costs they have spent performing the work. In the language of Earned Value, this is called the Actual Cost of Work Performed, or ACWP. As can be seen in this graphic, both the work scheduled, represented by the Budgeted Cost for Work Scheduled or BCWS and the work performed, represented by the Budgeted Cost for Work Performed or BCWP, are significantly under the ACWP. Funding from the customer on cost reimbursable contracts, however, is incrementally provided to contractor based on the contractor’s spending or actual cost AND the estimated costs to complete the scope of work. Performance to date and the remaining budget for work to complete are factors to consider when determining the EAC and future funding needs.
DOE is responsible to reimburse the contractor for all allowable costs up to the cost and funding limits established in the contract in accordance with FAR Clause 52.232-18, Limitations of Cost, for any fully funded cost-reimbursement contracts and 52.232-22 Limitations of Funds clause, as applicable for incrementally funded cost reimbursement contract.

## Slide 7: CONTRACT FUNDING
$
Time Now
BCWP
ACWP
EAC
Estimate To Complete
BCWS
BAC
Funding
Profile
Forecasted funding is aligned to the forecast of costs.
The Estimate to Complete (EAC), plus Contract Fee, is the total funding needed on the contract.
Notes: Funding is also forecasted in order to ensure that funds are available when necessary. This forecast of funding, therefore, is aligned to the forecast of actual costs. This is also called the Estimate to Complete, or ETC. The total amount of funding necessary on a cost reimbursable contract is equal to the Estimate at Completion, or EAC, plus the contract fee which is to be paid.

## Slide 8: BCWS vs. ETC
Budgeted Cost for Work Scheduled (BCWS)
  Time-phased budget spread of the required resources.
  Forms the Performance Measurement Baseline (PMB).
Estimate To Complete (ETC)
  Funding required to complete the remaining work.
  When added to ACWP it results in the EAC:
  ETC + ACWP = EAC
10-2323
Earned Value budgeting is the time-phased planning of the total resources required to satisfy the project’s contractual requirements
Notes: Earlier we listed some Earned Value terminology and abbreviations. We’ll now compare these to each other in order to determine which are budgets and which are funds.
The BCWS is the time-phased budget spread of the required resources. This forms the Performance Measurement Baseline.
The future BCWS is similar in nature to the Estimate to Complete, or ETC. While future BCWS represents the budget associated with future work scope, the ETC is the forecast of spending and necessary funding in order to pay for that work. If accomplishing the work results in a cost overrun or underrun, the ETC will be different than the future BCWS.
In all cases, adding the actual costs spent so far plus the cost planned in the future equals the Estimate at Complete.
In summary, earned value budgeting is the time-phased planning of the total resources required to satisfy the project’s contractual requirements.

## Slide 9: MANAGEMENT RESERVE vs CONTINGENCY
Management Reserve is BUDGET
  Part of the Contract Budget Baseline or Project Budget Base and traces to the Performance Measurement Baseline when applied (Green arrow)
Contingency is FUNDS (Red Arrow)
  Can be applied to FUND contractual changes, such as additional scope
  Can be applied as FUNDS to pay the bill, i.e. cost reimbursement type overruns
Notes: Management Reserve is controlled by the Contractor’s Project Manager and relates directly to budget. Management Reserve is within the Contract Budget Base or Project Budget Base and is applied to the Performance Measurement Baseline when authorized internal changes are made for which MR use is allowable.
Contingency, however, is controlled by the DOE and relates directly to funding. It may be applied to fund contractual changes to add scope and associated budget to the CBB or PBB, and it may be applied to pay the bill for cost overruns on Cost Reimbursement type contracts.

## Slide 10: BAC vs EAC
Budget At Completion (BAC)
  Budget representing ALL authorized work (i.e., the SOW)
  BAC cannot change without a change to the SOW, or appropriate approval of an OTB
Estimate At Completion (EAC)
  Funding value representing ALL the money that will be spent.
  Can change without a change to the SOW.
Notes: Note that both BAC and EAC end with the same letters. While BCWS, ACWP and ETC represent the time-phased values for budgets and funds, the BAC and EAC values are the At Completion numbers for budget and funds.
The BAC is the budget value for all authorized work scope. It ties directly to the total contract value, less profit or fee, plus any work that has been authorized but not yet negotiated. Since the BAC is directly tied to a project’s scope, it cannot be changed unless the scope also changes. The only exception to this is in an Over Target Baseline condition, which is discussed in Snippet 1-5.
The Estimate at Completion, however, is the spending necessary to perform all the project scope. In order to be comparable both the BAC and the EAC must have the same scope assumptions: One is a budget used as a metric and another a forecast of spending and necessary funding. An unlike the BAC, the EAC can change without a corresponding change to the project’s scope. However, if the scope does change the EAC typically changes as well.

## Slide 11: EXAMPLES OF BUDGET AND FUNDS CONFUSION
Cost Variance will continue until the Budget Request is approved.
Notes: We’ll finish this snippet with a series of confusing statements we have heard related to budgets and funds.
The first statement is “Cost variance will continue until the budget request is approved”. This is an alarming comment. Since budget requests are associated with scope, this statement implies that the contractor is working, and spending, on work that is not yet authorized.

## Slide 12: EXAMPLES OF BUDGET AND FUNDS CONFUSION
I am requesting Management Reserve to fix the overrun.
Notes: The statement “I am requesting Management Reserve to fix the overrun” violates the most basic rule for management reserve. It can never be used to eliminate variances caused by performance issues.

## Slide 13: EXAMPLES OF BUDGET AND FUNDS CONFUSION
This control account is behind schedule because invoices are being paid late.
Notes: Saying “This control account is behind schedule because invoices are being paid late” implies that performance, or BCWP, is being earned based on payments rather than work accomplishment. This would be acceptable if the invoices are being paid late because the work is behind schedule but stating it this way sends the wrong message. Work accomplishment should never be based on financial events like paying an invoice. Further, the contractor should be using estimated actuals based on the invoice amount in their EVMS to avoid false variances. Refer to Snippet 4-1 Estimated Actuals for more information.

## Slide 14: EXAMPLES OF BUDGET AND FUNDS CONFUSION
I underspent my budget.
Notes: Saying “I underspent my budget” is poor language. Budgets cannot be spent, only funds are spent, so budgets cannot be underspent. The better way to state this when the scope is being performed for less actual cost than budgeted would be to say “I am underrunning my budget”.

## Slide 15
The Management Reserve has been spent.
EXAMPLES OF BUDGET AND FUNDS CONFUSION
Notes: This example covers the statement “The Management Reserve has been spent”. Again, budget cannot be spent. Since management reserve is a budget element, it would be more correct to state “The management reserve has been depleted” or “there is no remaining MR”.

## Slide 16: EXAMPLES OF BUDGET AND FUNDS CONFUSION
Based on the amount spent, I’ll be out of budget by February.
Notes: And our last example of confusion is “Based on the amount spent, I’ll be out of budget by February”. We think we know what is meant here however running out of budget is NOT related to how much you have spent. A correct statement would be “Based on my spending rate, actual costs will exceed my total budget in February”.

## Slide 17: Summary
The System is predicated upon the concept of comparison:
  Budget that is planned and scheduled versus budget that is performed or ‘earned’, i.e. BCWS to BCWP
  Budget that is earned versus the funds it cost to complete, i.e. BCWP to ACWP.
  Budget planned to complete versus estimated funds to complete the effort, i.e. Budget at Completion versus Estimate At Completion.
If budgets and funds mix, the system fails.
Notes: Earned Value Management is a System of comparisons. The first component is Budget, the second is Funds. Both are essential to keep the system working. Yet they serve different purposes.
An Earned Value Management System is predicated upon the concept of comparisons of the budgets and the funds:
  Budget that is planned and scheduled versus budget that is performed or ‘earned’, i.e. BCWS to BCWP
  Budget that is earned versus the funds it cost to complete, i.e. BCWP to ACWP.
  Budget planned to complete versus estimated funds to complete the effort, i.e. Budget at Completion versus Estimate At Completion.
Understanding this concept is at the very heart of the system and must be maintained or the system fails.

## Slide 18
For additional information, please browse our library at the following Project Management Earned Value Management websites.
External:
https://www.energy.gov/projectmanagement/services-0/earned-value-management
Internal:
https://community.max.gov/display/DOEExternal/PM+EVM+Guidance
Notes: For additional information relative to EVMS procedures, templates, helpful references, more Snippets, and training materials, please refer to DOE PM’s external EVM Home page or the internal Max.Gov PM Library. Check back periodically for updated or new information.
Thank You for using the Snippet Library.